## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/20/25/01/NCP/ANP | RR/RDA/20/25/01 | Road from Thambuttegama - Nochchiyagama road to the road near the DIG's office of Thambuthegama Rajanganaya | Anuradhapura | Anuradhapura | Creates Consultant and Construction | 30% | 96940000 | 147079527.92 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-05 | 2026-09-03
RR/RDA/20/25/03/NCP/ANP | RR/RDA/20/25/03 | Thalawa - Eppawala margaye kele Amunukola handiyen aramba vee kele amunukola viddiyalayen divena margaya | Anuradhapura | Anuradhapura | Dissanayaka Builders | 40% | 26155768.37 | 41286372.1 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-04 | 2026-01-27 | 2026-06-30
RR/RDA/20/25/04/NCP/ANP | RR/RDA/20/25/04 | A - 9 maragayen aramba vee wale kade dakwa margaya | Anuradhapura | Anuradhapura | Dissanayaka Builders | 45% | 27008370.51 | 43911304.25 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-04 | 2026-01-27 | 2026-06-15
RR/RDA/20/25/06/NCP/ANP | RR/RDA/20/25/06 | Ududumbara boogas handiye sita sarakkugala pasal handiya dakwa margaya | Anuradhapura | Anuradhapura | Dissanayaka Builders | 0% | 26692661.01 | 44183866.35 | Awarded | Tender Below 50Mn |  |  |  | 2025-11-04 | 2026-01-27
RR/RDA/20/25/11/NCP/ANP | RR/RDA/20/25/11 | Palayakulama sita halmillakulama dakwa margaya | Anuradhapura | Anuradhapura | Dissanayaka Builders | 75% | 20887268.2 | 33233870.01 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-04 | 2026-01-27 | 2026-05-30
RR/RDA/20/25/16/NCP/ANP | RR/RDA/20/25/16 | Hiriwadunna handiye sita idigaswewa pansal handiya dakwa margaya | Anuradhapura | Maradankadawala | Sun Constructions (Pvt) Ltd. | 80% | 33000000 | 59684748.55 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-03 | 2026-03-04 | 2026-05-25
RR/RDA/20/25/18/NCP/ANP | RR/RDA/20/25/18 | Pahala Talawa road of Thalawa Andarawewa road | Anuradhapura | Anuradhapura | HPS Construction | 80% | 32443580.5 | 46999616.7 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-04-07 | 2026-06-30
RR/RDA/20/25/26/NCP/ANP | RR/RDA/20/25/26 | Development of IV lane from Nuwara Road to Mihinthalaya Road | Anuradhapura | Anuradhapura | Priyantha Civil Engineering | 6% | 29650453.29 | 38283840.94 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-10 | 2026-11-02
RR/RDA/20/25/28/NCP/ANP | RR/RDA/20/25/28 | Development of Rathnayake Mawatha | Anuradhapura | Anuradhapura | Priyantha Civil Engineering | 5% | 23041750.8 | 30142796.86 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-10 | 2026-02-11
RR/RDA/20/25/29/NCP/ANP | RR/RDA/20/25/29 | Development of the road from Udugama Colony rural road near the A9 road to the front of Mr. Somaratne Senanayake's house | Anuradhapura | Maradankadawala | Priyantha Civil Engineering | 0% | 27986392.06 | 32982943.17 | Awarded | Tender Below 50Mn |  |  |  | 2026-08-10 | 2026-11-02
| RR/RDA/20/25/53 | Development of road from Sripura main road to 38 Kolaniya Cemetery | Anuradhapura | Medawachchiya | NMST Contractor | 2% | 27971333.13 | 33546861.12 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-07-30 | 2026-10-22
| RR/RDA/20/25/54 | Development of road from Wahalkada D6 to Thalapakattialam on Punchimudagama road | Anuradhapura | Medawachchiya | Priyantha Civil Engineering | 5% | 33242915.64 | 40137233.68 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-10 | 2026-11-02
| RR/RDA/20/25/55 | Development of first phase of road from Punewa to Warakwewa | Anuradhapura | Medawachchiya | RSW Engineering | 25% | 29762232.5 | 34843454.4 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-07-29 | 2026-10-21
| RR/RDA/20/25/56 | Development of the road from Punewa Junction to Kudahalmillewa Lake | Anuradhapura | Medawachchiya | Priyantha Civil Engineering | 25% | 28506545 | 33620055.04 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-10 | 2026-11-02
| RR/RDA/20/25/57 | Development of the road from near Ikirigollawa Muslim Maha Vidyalaya to Ratmalgahawewa main road from near Ikirigollawa dam to Ratmalgahawa road | Anuradhapura | Medawachchiya | WGL Holdings | 30% | 10767548 | 14249058.84 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-10 | 2026-11-02
| RR/RDA/20/25/59 | From Makicchawa Junction to Temple (to Kulumiwakada Junction) | Anuradhapura | Medawachchiya | Priyantha Civil Engineering | 35% | 29006146.8 | 37056005 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-10 | 2026-11-02