## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/22/25/07/UP/BDL | RR/RDA/22/25/07 | Tharuna Govipola Margaye ithiri Kotasa Sanwardanaya Kirieema | Badulla | Bandarawela | Samadhi Construction | 0% | 13290035.01 | 15552666.77 | Awarded | Tender Below 50Mn |  |  |  | 2025-11-14 | 2026-02-13
RR/RDA/22/25/22/UP/BDL | RR/RDA/22/25/22 | Achchupatti Margaya | Badulla | Badulla | Priyankara Industries and Contractors | 20% | 25269262.7 | 30435860.35 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-06 | 2026-02-05