## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/15/25/02/EP/BTC | RR/RDA/15/25/02 | Concreting to Samurthi 1st Cross road | Batticaloa | Batticaloa | Kumaran Construction and Civil Works | 20% | 22158474.12 | 42354466.51 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2025-02-06 | 2026-02-15
RR/RDA/15/25/15/EP/BTC | RR/RDA/15/25/15 | Concrete to the Majma Nagar Mullivattuvan at paper town 210B | Batticaloa | Batticaloa | KMC Construction | 80% | 25270404.71 | 44093282.42 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06 | 2026-02-15
RR/RDA/15/25/05/EP/BTC | RR/RDA/15/25/05 | Concreting to Mailanthanai Sri Muththumariyamman Main Road | Batticaloa | Batticaloa | Kumaran Construction and Civil Works | 50% | 23225083.2 | 44365292.45 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06 | 2026-02-15
RR/RDA/15/25/09/EP/BTC | RR/RDA/15/25/09 | Concreting to NHDA Housing Scheme Internal Road 1st 2nd Cross | Batticaloa | Batticaloa | DKJ Construction | 40% | 7972333.63 | 16362900.23 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06 | 2026-02-15
RR/RDA/15/25/11/EP/BTC | RR/RDA/15/25/11 | Concreting to Kali Kovil Road | Batticaloa | Batticaloa | Jeezan Trading and Transport | 5% | 14105564 | 27925821.51 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06 | 2026-02-08
RR/RDA/15/25/12/EP/BTC | RR/RDA/15/25/12 | Concreting to Muthalaikuda to Munnaikkadu Boundary Road | Batticaloa | Batticaloa | Kumaran Construction and Civil Works | 40% | 26564874.51 | 47720744.3 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-21 | 2026-02-20 | 2026-02-15
RR/RDA/15/25/13/EP/BTC | RR/RDA/15/25/13 | Concreting to Sangarpuram- Vilavadi | Batticaloa | Batticaloa | Kumaran Construction and Civil Works | 10% | 24189660 | 46948339.52 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-21 | 2026-02-20 | 2026-02-15
RR/RDA/15/25/14/EP/BTC | RR/RDA/15/25/14 | Concreting to Agriculture Road | Batticaloa | Batticaloa | Jeezan Trading and Transport | 60% | 10593750 | 21690291.65 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06 | 2026-02-08
RR/RDA/15/25/10KM/01/BTC | RR/RDA/15/25/10KM/01 | Sooriya farm Road sathurukondan | Batticaloa | Batticaloa | Ganan Construction | 50% | 20565497.24 | 29978952.9 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-07-24 | 2026-10-23
RR/RDA/15/25/10KM/02/BTC | RR/RDA/15/25/10KM/02 | Iruthayapuram west 8th cross | Batticaloa | Batticaloa | Sanju Civil Construction | 30% | 27156544.25 | 37780902.59 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-07-24 | 2026-10-23
RR/RDA/15/25/10KM/07/BTC | RR/RDA/15/25/10KM/07 | Kanady cross Road to Magalingeshwarar kovil Road | Batticaloa | Batticaloa | Motec Engineering & Construction | 5% | 25946118 | 36198556.07 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-04 | 2026-11-03
RR/RDA/15/25/10KM/08/BTC | RR/RDA/15/25/10KM/08 | Poosakar Road, Kannakipuram, Mahiloor | Batticaloa | Batticaloa | Nathan's Construction | 95% | 27673151 | 40745256.81 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-07-24 | 2026-10-23
RR/RDA/15/25/10 |  | Concreting to Internal at MMV School | Batticaloa | Batticaloa |  | 95% | 33890314.66 | 33890314.66 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-11-15 | 2026-03-15