## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/07/25/02/SP/GAL | RR/RDA/07/25/02 | Delgahabedda-Kirimatiya Margaya | Galle | Galle | Dissanayaka Builders | 93% | 26404581.16 | 50069275.91 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2025-12-31
RR/RDA/07/25/05/SP/GAL | RR/RDA/07/25/05 | Atawalawatta Sri Rewatha Viduhala Idiripita Margaya | Galle | Galle | Dissanayaka Builders | 95% | 25809376.97 | 45727567.86 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-01-28
RR/RDA/07/25/09/SP/GAL | RR/RDA/07/25/09 | Panwila Hena Pradhana Margaya Lalith Mahathage Niwasa Asala Sita Manjula Jayaweera Mahathage Niwasa Dakwa Margaya | Galle | Hiniduma | DGSD Construction | 98% | 28039359.88 | 42959652.18 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-03-31
RR/RDA/07/25/17/SP/GAL | RR/RDA/07/25/17 | Dasa Kadaya Asala sita Jack Fruit Ceylon (Pvt) ayathanaya dakwa Margaya 1 Km carpert kirima | Galle | Galle | P.H. Engineering Construction (Pvt) Ltd | 47% | 20798250 | 33516218.38 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-01-30
RR/RDA/07/25/19/SP/GAL | RR/RDA/07/25/19 | SuriEla Margaya | Galle | Galle | A.D. Herath Engineering | 96% | 14387747 | 18573267.25 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-09 | 2026-01-08 | 2026-02-27