## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/03/25/12/WP/KTR | RR/RDA/03/25/12 | Concreting Batawala Road | Kalutara | Horana | Next Engineering Services (PVT) LTD | 39% | 18670236.2 | 26342506.07 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-22 | 2026-04-21
RR/RDA/03/25/16/WP/KTR | RR/RDA/03/25/16 | Development of carpeting of 1 km from Gane Aramba Road, Bogalla Junction to Ambepitiya Pinhena | Kalutara | Kalutara | Asela Construction | 0% | 27990360 | 37805645.98 | Awarded | Tender Below 50Mn |  |  |  | 2026-04-03 | 2026-07-03
| RR/RDA/03/25/17 | Development of 0.8 km carpeting of Newfa Mawatha | Kalutara | Kalutara | Develco Engineering (PVT) LTD | 0% | 6972603.95 | 8350944.75 | Awarded | Tender Below 50Mn |  |  |  | 2026-04-22 | 2026-07-22
RR/RDA/03/25/18/WP/KTR | RR/RDA/03/25/18 | Development of carpeting of the section (length 800 m) from near Minerithenna temple to Jananandanarama temple | Kalutara | Kalutara | Asela Construction | 0% | 17101775 | 23076319.79 | Awarded | Tender Below 50Mn |  |  |  | 2026-04-03 | 2026-07-03
| RR/RDA/03/25/19 | Carpeting and development of 500 meters of Moragahakanda watta Bodumaga Senasuna Viharastha Road | Kalutara | Kalutara | Develco Engineering (PVT) LTD | 55% | 8285619 | 9421190.92 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-04-22 | 2026-07-22
| RR/RDA/03/25/21 | Development of from Lewis Stadium to Heladiva Malshalawa | Kalutara | Kalutara | Develco Engineering (PVT) LTD | 55% | 15591781.1 | 18421245.76 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-04-22 | 2026-07-22