## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/04/25/13/CP/KY | RR/RDA/04/25/13 | Gonaala Pasala Asala Sita Kubukkadura Athuru Margayak Wana Gurumada Margaya | Kandy | Kundasale | Dharshana Construction | 37% | 35195820 | 42644514.03 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-05-08 | 2026-08-21 | 2026-08-21
RR/RDA/04/25/19/CP/KY | RR/RDA/04/25/19 | Mulgama viduhala Asala sita lewalan dakwa | Kandy | Gampola | The Wise Lanka Construction Company (Pvt) Ltd | 35% | 25917512.5 | 46131296.3 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-14 | 2026-03-31
RR/RDA/04/25/20/CP/KY | RR/RDA/04/25/20 | Carpeting road Ratemulla to Wendesiwaththa End | Kandy | Kandy | Wiscon (Pvt) Ltd | 45% | 36995817.1 | 40119276.86 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-08 | 2026-02-05 | 2026-03-20
RR/RDA/04/25/21/CP/KY | RR/RDA/04/25/21 | Galaha group sita finas kotasa Pahalagama-Ihalagama haraha nawa rohala dakwa Margaya | Kandy | Gampola | UGD Constructions | 80% | 22711029 | 40719533.36 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-17 | 2025-12-31 | 2026-03-10
RR/RDA/04/25/25/CP/KY | RR/RDA/04/25/25 | Delgasthenna Road | Kandy | Kundasale | NAGMA ENGINEERING (PVT) LTD | 0% | 56035922.24 | 78736509.47 | Awarded | Tender Above 50Mn |  |  |  | 2026-01-01 | 2026-05-06 | 2026-05-31
RR/RDA/04/25/28/CP/KY | RR/RDA/04/25/28 | Dehideniya sita Hedeniya dakwa Margaya | Kandy | Kandy | Senerath Engineering (pvt) Ltd | 35% | 38495776 | 41827394.04 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-25 | 2026-01-23 | 2026-04-10
RR/RDA/04/25/31(1)/CP/KY | RR/RDA/04/25/31(1) | Paththunupitiya School road to Gampola Road through Pallegama Anguruwala | Kandy | Gampola | Central Engineering Services Pvt Ltd. (CESL) | 30% | 50476865.28 | 65989182.36 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-03 | 2026-07-07 | 2026-10-31
RR/RDA/04/25/41/CP/KY | RR/RDA/04/25/41 | Karyala handiya pahala margya concrete kirima | Kandy | Gampola | UGD Constructions | 85% | 22047564 | 39022781.94 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-17 | 2026-01-14 | 2026-01-31
RR/RDA/04/25/52/CP/KY | RR/RDA/04/25/52 | Bokalawela Road from Hapugoda Junction to Ranawana (Drinage System Development and Road) | Kandy | Kandy | Senerath Engineering (pvt) Ltd | 60% | 50478905 | 72631674.77 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-21 | 2026-08-22
RR/RDA/04/25/53/CP/KY | RR/RDA/04/25/53 | Road from Amuvandeniya to Magurudeniya (development of the drainage and carpeting of the road) | Kandy | Kandy | Tiasa Construction (Pvt) Ltd | 40% | 29850460.2 | 39182935.51 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-05-08 | 2026-09-08
| RR/RDA/04/25/54 | Development of the Dolapihilla road from Navinnapitiya via Deldeniya | Kandy | Kandy | Ajith Construction | 20% | 65808186.5 | 73819405.52 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-06-08 | 2026-10-05
| RR/RDA/04/25/55 | Development of entrance roads, pedestrian rest areas and parking areas of the Sri Dalada Maligawa premises | Kandy | Kandy | Southern Group Civil Construction (Pvt) Ltd. | 40% | 83080000 | 98049399.56 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-06 | 2026-08-07