## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/25/25/02/SBP/KGL | RR/RDA/25/25/02 | Elagapitiya Colany Road From Debathgama Pallebage to Tea Shakthi Praja Shalawa | Kegalle | Kegalle | EHL Constructions | 85% | 36210751.61 | 52222845.54 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-03 | 2026-05-04
RR/RDA/25/25/03/SBP/KGL | RR/RDA/25/25/03 | From Kehelpannala Junction to Pahala Kabawita Road | Kegalle | Kegalle | SF Constructions | 95% | 71786959.2 | 96478103.45 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-30
RR/RDA/25/25/15/SBP/KGL | RR/RDA/25/25/15 | Moraliya Gagaboda Road | Kegalle | Ruwanwella | DHP Construction | 90% | 38093328.62 | 48285852.39 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-03 | 2026-02-01
RR/RDA/25/25/20/SBP/KGL | RR/RDA/25/25/20 | Neluwakkana gama meda Road | Kegalle | Ruwanwella | Loshitha Construction | 95% | 23823804.13 | 33221060.47 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-20 | 2026-02-18
RR/RDA/25/25/28/SBP/KGL | RR/RDA/25/25/28 | Naagas thenna Road | Kegalle | Ruwanwella | Jayasinghe Contractors (Pvt) Ltd. | 90% | 102000742.36 | 103886540.99 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-11 | 2026-08-12
RR/RDA/25/25/34/SBP/KGL | RR/RDA/25/25/34 | Road Connecting Ihala Palampitiya and Pahala Palampitiya | Kegalle | Ruwanwella | DKS Nishantha Construction | 0% | 26331747.62 | 36648120.48 | Awarded | Tender Below 50Mn |  |  |  | 2026-07-24 | 2026-10-22
RR/RDA/25/25/35/SBP/KGL | RR/RDA/25/25/35 | Kudadeniya Adurapola Watta Road | Kegalle | Ruwanwella | TMT Construction | 60% | 29362927.93 | 41661137.53 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-04 | 2026-06-02
RR/RDA/25/25/38/SBP/KGL | RR/RDA/25/25/38 | Development of the road near the closed tea factory on Edurapola Watta main road | Kegalle | Ruwanwella | TMT Construction | 95% | 22209331.1 | 30599205.16 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-04 | 2026-06-04
RR/RDA/25/25/39/SBP/KGL | RR/RDA/25/25/39 | Development of Gatayamulla Jagatpura Pannala Rasnadeniya road | Kegalle | Ruwanwella | Samindra Construction | 95% | 31491651.4 | 32775992.83 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-06-02 | 2026-08-31 | 2026-08-31
RR/RDA/25/25/40/SBP/KGL | RR/RDA/25/25/40 | Kabagamuwa 17 Acres Road Development | Kegalle | Ruwanwella | TMT Construction | 95% | 14823379.41 | 18604688.76 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-28 | 2026-05-28