## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/21/25/03/NCP/POL | RR/RDA/21/25/03 | Mahasenpura pradeepika kadaya asala sita Katukeliyawa dakwa margaya Carpart kireema | Polonnaruwa | Habarana | Nadun Construction (Pvt) Ltd | 80% | 33480137.33 | 53473343.43 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-10 | 2026-03-11 | 2026-04-10
RR/RDA/21/25/17/NCP/POL | RR/RDA/21/25/26 | Development of the road from Kaduruwela Muslim Kolaniya road to Pachcha Palliya | Polonnaruwa | Polonnaruwa | Central Engineering Services Pvt Ltd. (CESL) | 80% | 53880000 | 75598504.72 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-05-25 | 2026-08-24 | 2026-10-31
RR/RDA/21/25/17/NCP/POL | RR/RDA/21/25/27 | Development of 1 canal Road from Kadurwela Muslim Kolaniya Road to Parakum Mawatha | Polonnaruwa | Polonnaruwa | Nadun Construction (Pvt) Ltd | 45% | 54640000 | 62351983.93 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-07-02 | 2026-10-01