## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/17/25/09/EP/TRN | RR/RDA/17/25/09 | School-Galmetiyawa Main Internal Road | Trincomalee | Trincomalee | Zaka Engineering Consultancy | 50% | 53122107.5 | 77200000 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-05-22 | 2026-08-21 | 2026-07-31
RR/RDA/17/25/11/EP/TRN | RR/RDA/17/25/11 | Development of Road from near the Fair | Trincomalee | Trincomalee | MS Construction | 15% | 25280343.6 | 37892493.36 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-06-04 | 2026-09-03
RR/RDA/17/25/19/EP/TRN | RR/RDA/17/25/19 | Periya Suwami Kovil Road-Concrete | Trincomalee | Trincomalee | Motec Engineering & Construction | 20% | 25774146 | 39914113.43 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-06-04 | 2026-09-03
RR/RDA/SP/17/25/03/EP/TRN | RR/RDA/SP/17/25/03 | Hajra Road (Alhira Jalaira Road) | Trincomalee | Trincomalee | STAAR Construction | 40% | 38692742 | 51948669.36 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-05-22 | 2026-08-21
RR/RDA/17/25/10KM/04/EP/TRN | RR/RDA/17/25/10KM/04 | Kajuwaththa gama meda road | Trincomalee | Trincomalee | NMST Construction | 5% | 22770000 | 29466015.3 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-07-31 | 2026-10-29
RR/RDA/17/25/10KM/06/EP/TRN | RR/RDA/17/25/10KM/06 | Budu pilima and 4th lane road | Trincomalee | Trincomalee | RS Construction | 15% | 17520285.64 | 28351870.49 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-07-31 | 2026-10-29
RR/RDA/17/25/10KM/08/EP/TRN | RR/RDA/17/25/10KM/08 | Paththini Amman Kevil road | Trincomalee | Trincomalee | Alpha Engineering Services & Suppliers | 25% | 30365709 | 46089014.73 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-04 | 2026-11-03
RR/RDA/17/25/10KM/09/EP/TRN | RR/RDA/17/25/10KM/09 | Bazar mosque road | Trincomalee | Trincomalee | MTA Construction | 40% | 32616074.7 | 44293054.87 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-04 | 2026-11-03
RR/RDA/17/25/08 |  | Concreting of Play Ground Road Mahadiulwewa Stage II | Trincomalee | Trincomalee |  | 90% | 43210842.75 | 43210842.75 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-02-02 | 2026-03-31 | 2026-03-31