## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/16/25/10KM/08/AKK/AKK | RR/RDA/16/25/10KM/08 | RDS Road Addalachena 6, 8 | Ampara | Akkaraipattu | MLH & sons Construction | 0% | 18326682.5 | 29731841.59 | Awarded | Tender Below 50Mn |  |  |  | 2026-02-26 | 2026-05-27
RR/RDA/16/25/10KM/13/AKK/AKK | RR/RDA/16/25/10KM/13 | Jaica - Tsunami Village Road | Ampara | Akkaraipattu | Gama Construction & Consultant pvt Ltd | 70% | 26167747.32 | 39951889.78 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-15 | 2026-06-13