## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/SP/16/25/01/AKK/AMP | RR/RDA/SP/16/25/01 | Rectification and Asphalt Surfacing on Ambahagawela -Namaloya Main Road | Ampara | Ampara | SMA Careem Engineering Consultancy Services & Suppliers (Pvt) Ltd | 34% | 222189859.13 | 306475548.92 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-31 | 2026-06-30
RR/RDA/16/25/10KM/02/AKK/AMP | RR/RDA/16/25/10KM/02 | Road from Nelum Cafe Junction to Neeththa | Ampara | Ampara | Gama Construction & Consultant pvt Ltd | 20% | 19318560.1 | 29760217.62 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-07 | 2026-06-05
RR/RDA/16/25/10KM/04/AKK/AMP | RR/RDA/16/25/10KM/04 | Vevinna Boogas Junction Inner Road | Ampara | Ampara | Gama Construction & Consultant pvt Ltd | 15% | 9692957.45 | 14460000 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-07 | 2026-05-08
RR/RDA/16/25/10KM/05/AKK/AMP | RR/RDA/16/25/10KM/05 | Road from Dorapaha Junction to Navagiriya Lake | Ampara | Ampara | Ema Constructions (Pvt) Ltd | 10% | 18058942 | 28554939.58 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-09 | 2026-06-07