## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/01/25/14/WP/COL | RR/RDA/01/25/14 | Development of the section from Arangala Bridge to Mihindu Mawatha in Malabe West Division | Colombo | Colombo | W.A. Perera & Company (Pvt) Ltd. | 68% | 33591596.5 | 51359519.36 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-10 | 2026-05-12
RR/RDA/01/25/30/WP/COL | RR/RDA/01/25/30 | Development of the road from near the transformer near Seebara Kade, Boralugoda to the Jayanthi Road | Colombo | Colombo | Asset Engineering (Pvt)LTD | 0% | 21619184.95 | 22641802.22 | Awarded | Tender Below 50Mn |  |  |  | 2026-07-30 | 2026-08-29