## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/10/25/06/NP/JFN | RR/RDA/10/25/06 | Renovation of West beach Road | Jaffna | Jaffna | Sun Constructions (Pvt) Ltd. | 10% | 83618425 | 91211155.29 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-17 | 2026-04-18 | 2026-07-31
RR/RDA/10/25/14/NP/JFN | RR/RDA/10/25/14 | Pankuru Veethy | Jaffna | Jaffna | Thaaru Construction | 60% | 32829728.8 | 47295898.62 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-05-26 | 2026-05-26
RR/RDA/10/25/18/NP/JFN | RR/RDA/10/25/18 | Atchuvely Industrial Road | Jaffna | Jaffna | Sun Constructions (Pvt) Ltd. | 70% | 72500000 | 101707442.89 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-03 | 2026-04-04 | 2026-05-31