## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/04/25/13/CP/KY | RR/RDA/04/25/13 | Gonaala Pasala Asala Sita Kubukkadura Athuru Margayak Wana Gurumada Margaya | Kandy | Kundasale | Dharshana Construction | 37% | 35195820 | 42644514.03 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-05-08 | 2026-08-21 | 2026-08-21
RR/RDA/04/25/25/CP/KY | RR/RDA/04/25/25 | Delgasthenna Road | Kandy | Kundasale | NAGMA ENGINEERING (PVT) LTD | 0% | 56035922.24 | 78736509.47 | Awarded | Tender Above 50Mn |  |  |  | 2026-01-01 | 2026-05-06 | 2026-05-31