## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/18/25/11/NWP/KRG | RR/RDA/18/25/11 | Development of road from Dambulu Road to Havanathenna via Ehelagollaya | Kurunegala | Kurunegala | Shanho Enterprises Pvt Ltd. | 65% | 46193949.68 | 64750199.52 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-04 | 2026-07-01 | 2026-08-01
RR/RDA/18/25/135/NWP/KRG | RR/RDA/18/25/135 | Kelegedara Gamameda Road (CTB Basaya Dawanaya wana) Kavudumunna, Kunumade, Hungan pitiya haraha diwena Margaya Kapat Kirima | Kurunegala | Kurunegala | Jayasinghe Contractors (Pvt) Ltd. | 20% | 41750386.7 | 55779764.12 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-20 | 2026-05-20 | 2026-05-20
RR/RDA/18/25/137/NWP/KRG | RR/RDA/18/25/137 | Damunugolla Sita Kobbewehera Handiya Dakwa Margaya Kapat Kirima | Kurunegala | Kurunegala | W P J Engineering(Pvt)Ltd | 45% | 18425029.46 | 23865719.81 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-07 | 2026-04-06 | 2026-06-06
RR/RDA/18/25/138/NWP/KRG | RR/RDA/18/25/138 | Pudukkulama Bogas Handiye sita Keppitiya haraha Thihawa Dakwa Margaya Kapat Kirima | Kurunegala | Kurunegala | W P J Engineering(Pvt)Ltd | 20% | 30650394.06 | 39359193.23 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-07 | 2026-04-07 | 2026-06-07
RR/RDA/18/25/139/NWP/KRG | RR/RDA/18/25/139 | Akkara Panaha Mansandiye Sita Walahamulla Dakwa Margaya | Kurunegala | Kurunegala | Jayawansa Construction (PVT) Ltd | 90% | 28112995.75 | 41102824.35 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-17 | 2026-05-18 | 2026-06-18