## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/20/25/16/NCP/ANP | RR/RDA/20/25/16 | Hiriwadunna handiye sita idigaswewa pansal handiya dakwa margaya | Anuradhapura | Maradankadawala | Sun Constructions (Pvt) Ltd. | 80% | 33000000 | 59684748.55 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-03 | 2026-03-04 | 2026-05-25
RR/RDA/20/25/29/NCP/ANP | RR/RDA/20/25/29 | Development of the road from Udugama Colony rural road near the A9 road to the front of Mr. Somaratne Senanayake's house | Anuradhapura | Maradankadawala | Priyantha Civil Engineering | 0% | 27986392.06 | 32982943.17 | Awarded | Tender Below 50Mn |  |  |  | 2026-08-10 | 2026-11-02