## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/02/25/03/WP/GMP | RR/RDA/02/25/03 | Development of De silva road beginning from Angurukaramulla temble road to Negombo Colombo road | Gampaha | Negombo | Dilini Builders (PVT) LTD | 0% | 5430100 | 6886574.13 | Awarded | Tender Below 50Mn |  |  |  | 2026-06-29 | 2026-09-28
| RR/RDA/02/25/10 | The road from Thaladuwa Road near Negombo Bus Stand, passing Jude Church, to the cemetery | Gampaha | Negombo | Dilini Builders (PVT) LTD | 0% | 35997890 | 43987022.27 | Awarded | Tender Below 50Mn |  |  |  | 2026-05-13 | 2026-08-12
| RR/RDA/02/25/19 | 3 A road carpeted development near the Japanese Montessori at the junction of the North Kadirana Division. | Gampaha | Negombo | Jeyanthan Construction | 0% | 15141484.5 | 21486157.55 | Awarded | Tender Below 50Mn |  |  |  | 2026-04-21 | 2026-07-21
| RR/RDA/02/25/24 | Near Urapana Sisira Coir Mill to Hapugahagama Co-operative | Gampaha | Negombo | Jeyanthan Construction | 0% | 19032750 | 26884145.14 | Awarded | Tender Below 50Mn |  |  |  | 2026-04-10 | 2026-07-10