## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/04/25/13/CP/KY | RR/RDA/04/25/13 | Gonaala Pasala Asala Sita Kubukkadura Athuru Margayak Wana Gurumada Margaya | Kandy | Kundasale | Dharshana Construction | 37% | 35195820 | 42644514.03 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-05-08 | 2026-08-21 | 2026-08-21
RR/RDA/04/25/19/CP/KY | RR/RDA/04/25/19 | Mulgama viduhala Asala sita lewalan dakwa | Kandy | Gampola | The Wise Lanka Construction Company (Pvt) Ltd | 35% | 25917512.5 | 46131296.3 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-14 | 2026-03-31
RR/RDA/04/25/20/CP/KY | RR/RDA/04/25/20 | Carpeting road Ratemulla to Wendesiwaththa End | Kandy | Kandy | Wiscon (Pvt) Ltd | 45% | 36995817.1 | 40119276.86 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-08 | 2026-02-05 | 2026-03-20
RR/RDA/04/25/21/CP/KY | RR/RDA/04/25/21 | Galaha group sita finas kotasa Pahalagama-Ihalagama haraha nawa rohala dakwa Margaya | Kandy | Gampola | UGD Constructions | 80% | 22711029 | 40719533.36 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-17 | 2025-12-31 | 2026-03-10
RR/RDA/04/25/25/CP/KY | RR/RDA/04/25/25 | Delgasthenna Road | Kandy | Kundasale | NAGMA ENGINEERING (PVT) LTD | 0% | 56035922.24 | 78736509.47 | Awarded | Tender Above 50Mn |  |  |  | 2026-01-01 | 2026-05-06 | 2026-05-31
RR/RDA/04/25/28/CP/KY | RR/RDA/04/25/28 | Dehideniya sita Hedeniya dakwa Margaya | Kandy | Kandy | Senerath Engineering (pvt) Ltd | 35% | 38495776 | 41827394.04 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-25 | 2026-01-23 | 2026-04-10
RR/RDA/04/25/31(1)/CP/KY | RR/RDA/04/25/31(1) | Paththunupitiya School road to Gampola Road through Pallegama Anguruwala | Kandy | Gampola | Central Engineering Services Pvt Ltd. (CESL) | 30% | 50476865.28 | 65989182.36 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-03 | 2026-07-07 | 2026-10-31
RR/RDA/04/25/41/CP/KY | RR/RDA/04/25/41 | Karyala handiya pahala margya concrete kirima | Kandy | Gampola | UGD Constructions | 85% | 22047564 | 39022781.94 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-17 | 2026-01-14 | 2026-01-31
RR/RDA/04/25/52/CP/KY | RR/RDA/04/25/52 | Bokalawela Road from Hapugoda Junction to Ranawana (Drinage System Development and Road) | Kandy | Kandy | Senerath Engineering (pvt) Ltd | 60% | 50478905 | 72631674.77 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-21 | 2026-08-22
RR/RDA/04/25/53/CP/KY | RR/RDA/04/25/53 | Road from Amuvandeniya to Magurudeniya (development of the drainage and carpeting of the road) | Kandy | Kandy | Tiasa Construction (Pvt) Ltd | 40% | 29850460.2 | 39182935.51 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-05-08 | 2026-09-08
| RR/RDA/04/25/54 | Development of the Dolapihilla road from Navinnapitiya via Deldeniya | Kandy | Kandy | Ajith Construction | 20% | 65808186.5 | 73819405.52 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-06-08 | 2026-10-05
| RR/RDA/04/25/55 | Development of entrance roads, pedestrian rest areas and parking areas of the Sri Dalada Maligawa premises | Kandy | Kandy | Southern Group Civil Construction (Pvt) Ltd. | 40% | 83080000 | 98049399.56 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-06 | 2026-08-07
RR/RDA/05/25/09/CP/MTL | RR/RDA/05/25/09 | Ilukkumbura Samurdhi karyalaya asala Patti ela pilama dakwa | Matale | Matale | Pragathi Civil Contractor | 80% | 38748820 | 41365188.3 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-23 | 2026-02-15
RR/RDA/05/25/10/CP/MTL | RR/RDA/05/25/10 | Sonuththa pradana margaye Shailatharamaya idiriye sita 80 yaya dakwa | Matale | Nalanda | NAGMA ENGINEERING (PVT) LTD | 70% | 56167707.75 | 79104652.3 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-24 | 2026-04-27 | 2026-05-31
RR/RDA/05/25/11/CP/MTL | RR/RDA/05/25/11 | Hunukete sita Elagala dakwa Pradana Margaya | Matale | Matale | Senerath Engineering (pvt) Ltd | 50% | 82470143.89 | 108683600.82 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-06 | 2026-03-26 | 2026-05-20
RR/RDA/05/25/26/CP/MTL | RR/RDA/05/25/26 | Pallepola saukya karyalaye sita ekamuthugama dakwa margaya | Matale | Nalanda | Jayaru Engineering (Pvt) Ltd | 60% | 18760083.54 | 30575367.23 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-01 | 2025-12-31 | 2026-03-25
RR/RDA/05/25/30/CP/MTL | RR/RDA/05/25/30 | Ganadewi pilimaya asala Kulathunga mahathage welanda sala dakwa | Matale | Nalanda | Lahiru Construction & Consultants (PVT) Ltd | 60% | 59540000 | 77270301.29 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-10 | 2026-08-10 | 2026-08-10
RR/RDA/06/25/32/CP/NE | RR/RDA/06/25/32 | Nanuoya Glaso pahala kotasa Margaya | Nuwara Eliya | Nuwara Eliya | wiscon (pvt) ltd | 5% | 38841280.5 | 43085721.61 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-26 | 2026-05-20
RR/RDA/06/25/34/CP/NE | RR/RDA/06/25/34 | Udupussellawa margaye Amasta handiye sita Ambagasdowa dakwa Margaya | Nuwara Eliya | Hanguranketha | NAGMA ENGINEERING (PVT) LTD | 0% | 54639783.83 | 84599211.7 | Awarded | Tender Above 50Mn |  |  |  | 2026-01-01 | 2026-05-06
RR/RDA/06/25/38/CP/NE | RR/RDA/06/25/38 | Ketahira Gallella margya palama haraha Udagama dakwa Margaya | Nuwara Eliya | Hanguranketha | NAGMA ENGINEERING (PVT) LTD | 0% | 38465634.79 | 54713411.13 | Awarded | Tender Above 50Mn |  |  |  | 2026-01-01 | 2026-05-06
RR/RDA/06/25/40/CP/NE | RR/RDA/06/25/40 | Walapane Samachaithya asalin Arambawana Kurundu oya diyaella dakwa Margaya | Nuwara Eliya | Hanguranketha | UGD Constructions | 10% | 31672222.12 | 35044851.53 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-09 | 2026-01-31
RR/RDA/06/25/41/CP/NE | RR/RDA/06/25/41 | Nayapana Gammada tharapara sanwardhanaya | Nuwara Eliya | Nuwara Eliya | Central Engineering Services Pvt Ltd. (CESL) | 35% | 51754603.52 | 64794731.2 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-28 | 2026-07-29
RR/RDA/06/25/42/CP/NE | RR/RDA/06/25/42 | AC Overlaying from Polpitiya Junction to 04th Mile Post (CH 3+700 – 8+700 km) | Nuwara Eliya | Norwood | UKS Lanka Engineering Pvt Ltd. | 50% | 220116957.84 | 276005265.17 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-11-24 | 2026-08-22 | 2026-08-22
| RR/RDA/06/25/45 | Carpeting of road from Bambaragama Moragollahinna to Karamidula | Nuwara Eliya | Hanguranketha | Ajith Construction | 10% | 61551869.38 | 68311664.39 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-05 | 2026-06-05
| RR/RDA/06/25/46 | Carpeting of Mahathenna to Hapugasdeniya Main Road | Nuwara Eliya | Hanguranketha | Ajith Construction | 73% | 68070000 | 79957655.08 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-05 | 2026-06-05
RR/RDA/06/25/44 |  | Carpeting of Muloya Main Road Section 2 | Nuwara Eliya | Hanguranketha |  | 60% | 42312390.95 | 42312390.95 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-22 | 2025-12-31 | 2026-03-15
RR/RDA/06/25/47 |  | Carpeting of the road from Gatakula to Madanwala via Diaudagama, Kottala | Nuwara Eliya | Hanguranketha |  | 38% | 28020844.83 | 28020844.83 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 | 2025-12-31 | 2026-03-15
RR/RDA/05/25/23 |  | Manchanayake shed eka asala sita sampath waththa haraha Galketiyawa margaya | Matale | Nalanda |  | 60% | 28401905.12 | 28401905.12 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-12-13 | 2026-06-13
RR/RDA/05/25/28 |  | Adawala Udagama Road | Matale | Nalanda |  | 75% | 56161142.68 | 56161142.68 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2025-09-22 | 2026-02-22 | 2026-04-20