## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/10/25/06/NP/JFN | RR/RDA/10/25/06 | Renovation of West beach Road | Jaffna | Jaffna | Sun Constructions (Pvt) Ltd. | 10% | 83618425 | 91211155.29 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-17 | 2026-04-18 | 2026-07-31
RR/RDA/10/25/14/NP/JFN | RR/RDA/10/25/14 | Pankuru Veethy | Jaffna | Jaffna | Thaaru Construction | 60% | 32829728.8 | 47295898.62 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-05-26 | 2026-05-26
RR/RDA/10/25/18/NP/JFN | RR/RDA/10/25/18 | Atchuvely Industrial Road | Jaffna | Jaffna | Sun Constructions (Pvt) Ltd. | 70% | 72500000 | 101707442.89 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-03 | 2026-04-04 | 2026-05-31
RR/RDA/10/25/22/NP/JFN | RR/RDA/10/25/22 | Anaivilunthan Sudalai Road | Jaffna | Point Pedro | Yaso Engineering | 65% | 48082026.3 | 61126170.56 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-02 | 2026-04-03 | 2026-06-03
RR/RDA/10/25/25/NP/JFN | RR/RDA/10/25/25 | Palaiya Vaikal Veeethy | Jaffna | Point Pedro | Sun Constructions (Pvt) Ltd. | 50% | 54450000 | 79703717.02 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-02 | 2026-06-15
RR/RDA/12/25/01/NP/VVN | RR/RDA/12/25/01 | Thiruchchenthooran mill road NVSTE541 | Vavuniya | Vavuniya | TMC Constructions | 0% | 53290000 | 100688815.19 | Awarded | Tender Above 50Mn |  |  |  | 2026-07-01 | 2026-09-29
RR/RDA/12/25/03/NP/VVN | RR/RDA/12/25/03 | Puthiya manipuram, main road (NVSTE481) | Vavuniya | Vavuniya | Yaso Engineering | 35% | 32481108 | 41435979.42 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-13
RR/RDA/12/25/04/NP/VVN | RR/RDA/12/25/04 | Suntharapuram main road | Vavuniya | Vavuniya | Sun Constructions (Pvt) Ltd. | 35% | 162703000 | 71964095.93 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-05 | 2026-06-03
RR/RDA/12/25/17/NP/VVN | RR/RDA/12/25/17 | Lyca village enterance Road | Vavuniya | Vavuniya | Sun Constructions (Pvt) Ltd. | 35% | 0 | 54064384.24 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-05 | 2026-06-03
RR/RDA/12/25/22/NP/VVN | RR/RDA/12/25/22 | Mannankerny road | Vavuniya | Vavuniya | Sun Constructions (Pvt) Ltd. | 50% | 0 | 51515196.2 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-05 | 2026-06-03
RR/RDA/12/25/52/NP/VVN | RR/RDA/12/25/52 | Menanager Malakattu Kalkuwari Road | Vavuniya | Vavuniya | Sun Constructions (Pvt) Ltd. | 65% | 0 | 54861523.89 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-05 | 2026-06-03
RR/RDA/12/25/07/NP/VVN | RR/RDA/12/25/07 | Tharanikulam main road | Vavuniya | Vavuniya | Sintha Construction (Pvt) Ltd | 70% | 20876280.7 | 30580213.01 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/10/NP/VVN | RR/RDA/12/25/10 | Achchipuram amman temble road | Vavuniya | Vavuniya | Ancheneya Constructions | 70% | 19430799.3 | 28181354.24 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06
RR/RDA/12/25/12/NP/VVN | RR/RDA/12/25/12 | Nanthimiththiragama 1st | Vavuniya | Vavuniya | Ancheneya Constructions | 5% | 24583111.3 | 30752460 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-20 | 2026-05-22
RR/RDA/12/25/13/NP/VVN | RR/RDA/12/25/13 | Nanthimiththiragama 2nd | Vavuniya | Vavuniya | Ancheneya Constructions | 5% | 24829841.3 | 31291948.01 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-20 | 2026-04-22
RR/RDA/12/25/14/NP/VVN | RR/RDA/12/25/14 | Nanthimiththiragama 4th | Vavuniya | Vavuniya | Ancheneya Constructions | 5% | 25113641.3 | 30939872.36 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-20 | 2026-04-22
RR/RDA/12/25/18/NP/VVN | RR/RDA/12/25/18 | Nedunkerny North sandankulam Road | Vavuniya | Vavuniya | Yaso Engineering | 35% | 32829160.1 | 46839314.91 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-12
RR/RDA/12/25/19/NP/VVN | RR/RDA/12/25/19 | Senaipilavu Road | Vavuniya | Vavuniya | Yaso Engineering | 70% | 32576225 | 43285227.82 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-12
RR/RDA/12/25/20/NP/VVN | RR/RDA/12/25/20 | Puthiyakudiyiruppu parasankulam road | Vavuniya | Vavuniya | Bapithan Construction | 70% | 23259239.3 | 34966229.53 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06
RR/RDA/12/25/21/NP/VVN | RR/RDA/12/25/21 | Bagaswewa 01st 22nd lane | Vavuniya | Vavuniya | Bapithan Construction | 35% | 22749983.3 | 33747516.65 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06
RR/RDA/12/25/24/NP/VVN | RR/RDA/12/25/24 | Kanagarayankulam puthuvilankulam road (NVVNE073) | Vavuniya | Vavuniya | Bapithan Construction | 70% | 31165786.3 | 46468981.72 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-13
RR/RDA/12/25/25/NP/VVN | RR/RDA/12/25/25 | 2nd cross Lane Ginigathhena | Vavuniya | Vavuniya | Nimna Holdings (Pvt) Ltd | 70% | 27770291 | 40686140.26 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-17 | 2026-02-21
RR/RDA/12/25/27/NP/VVN | RR/RDA/12/25/27 | From Acre 400 7th Lane to cross end of the 2nd internal road close to Andarawewa | Vavuniya | Vavuniya | Ranasinghe Construction | 30% | 46360659.24 | 57948785.02 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-02 | 2026-03-03
RR/RDA/12/25/28/NP/VVN | RR/RDA/12/25/28 | From Janaudanagama 2nd internal road to end of the free school | Vavuniya | Vavuniya | North Construction (Pvt) Ltd | 35% | 26569012.25 | 37396800.47 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06
RR/RDA/12/25/29/NP/VVN | RR/RDA/12/25/29 | Kalasiyambalawa Road | Vavuniya | Vavuniya | North Construction (Pvt) Ltd | 50% | 13504281.45 | 19583811.27 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-13
RR/RDA/12/25/31/NP/VVN | RR/RDA/12/25/31 | Mahakachchakodiya to Ettambagaskada | Vavuniya | Vavuniya | Yansika Construction | 30% | 45254190.85 | 59974624.42 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-02 | 2026-01-20
RR/RDA/12/25/35/NP/VVN | RR/RDA/12/25/35 | Awusadapitiya Pubudugama Road | Vavuniya | Vavuniya | Nimna Holdings (Pvt) Ltd | 70% | 32504637.43 | 46347432.25 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-02 | 2026-02-21
RR/RDA/12/25/38/NP/VVN | RR/RDA/12/25/38 | Salalinigama 11 lane | Vavuniya | Vavuniya | Sintha Construction (Pvt) Ltd | 50% | 30830906.7 | 40853027.3 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/40/NP/VVN | RR/RDA/12/25/40 | Halabagaswewa | Vavuniya | Vavuniya | North Construction (Pvt) Ltd | 5% | 25032191.25 | 36283467.53 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/43/NP/VVN | RR/RDA/12/25/43 | Pavatkulam tack 5 vaarikuttiyoor | Vavuniya | Vavuniya | North Construction (Pvt) Ltd | 70% | 17351705.25 | 25717072.9 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/48/NP/VVN | RR/RDA/12/25/48 | Mukaththankulam 7th lane (NVVPE173) | Vavuniya | Vavuniya | Sintha Construction (Pvt) Ltd | 70% | 18900081.2 | 28294497.45 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/51/NP/VVN | RR/RDA/12/25/51 | Adappankulam aladi road | Vavuniya | Vavuniya | North Construction (Pvt) Ltd | 70% | 13383862.25 | 19573472.29 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/54/NP/VVN | RR/RDA/12/25/54 | Nikawewa Right Village Road | Vavuniya | Vavuniya | Yansika Construction | 70% | 17143053.95 | 22922029.4 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-05
RR/RDA/12/25/60/NP/VVN | RR/RDA/12/25/60 | Salalinigama lane 12 | Vavuniya | Vavuniya | Sintha Construction (Pvt) Ltd | 15% | 23397220 | 33827661.22 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-04-03 | 2026-07-03
RR/RDA/12/25/62/NP/VVN | RR/RDA/12/25/62 | Periyavilathikulam | Vavuniya | Vavuniya | Omega Construction (Pvt) Ltd | 35% | 16916712.5 | 23338487.33 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-04-03 | 2026-07-03
RR/RDA/12/25/63/NP/VVN | RR/RDA/12/25/63 | 1st Cross Street Alakarai Road | Vavuniya | Vavuniya | North Construction | 30% | 38912500 | 55600429.77 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-20 | 2026-05-21
RR/RDA/12/25/64/NP/VVN | RR/RDA/12/25/64 | Nedunkulama | Vavuniya | Vavuniya | Arul Selvi Construction and Hardware | 70% | 15902966.56 | 22278087.37 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-04-03 | 2026-07-03
RR/RDA/13/25/01/NP/MUL | RR/RDA/13/25/01 | Akkaraiveli Paraiyanaru ( Vilaththiyad) Road Package 1 | Mullaitivu | Mullaitivu | Sun Constructions (Pvt) Ltd. | 0% | 145000000 | 188808095.02 | Awarded | Tender Above 50Mn |  |  |  | 2025-12-02 | 2026-03-02
RR/RDA/13/25/03/NP/MUL | RR/RDA/13/25/03 | Navatkadu Road | Mullaitivu | Mullaitivu | TMC Constructions | 60% | 50363687 | 77969519 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-01 | 2026-06-06
RR/RDA/13/25/06/NP/MUL | RR/RDA/13/25/06 | Pandaravanniyan Silaiyadi Road | Mullaitivu | Mullaitivu | Sun Constructions (Pvt) Ltd. | 40% | 83700000 | 113438730.78 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-26 | 2026-03-26
RR/RDA/13/25/07/NP/MUL | RR/RDA/13/25/07 | Kanagarayankulam District Boundary Road (Old Kandy road) | Mullaitivu | Mullaitivu | Sun Constructions (Pvt) Ltd. | 60% | 159972500 | 220671169.9 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-26 | 2026-03-26 | 2026-06-12
RR/RDA/13/25/08/NP/MUL | RR/RDA/13/25/08 | Kumulamunai Akkarayan road | Mullaitivu | Mullaitivu | Nimna Holdings (Pvt) Ltd | 70% | 148861042 | 198505802.7 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-01 | 2026-06-20
RR/RDA/13/25/10/NP/MUL | RR/RDA/13/25/10 | Pandiyankulam Neddankandal Road | Mullaitivu | Mullaitivu | Nimna Holdings (Pvt) Ltd | 70% | 144696282.5 | 191627958.51 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-01 | 2026-06-10
RR/RDA/13/25/11/NP/MUL | RR/RDA/13/25/11 | Ethawetuvuwewa to Sampathnuwara | Mullaitivu | Mullaitivu | Nimna Holdings (Pvt) Ltd | 30% | 110422944.5 | 141810206.62 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-22 | 2026-06-22
RR/RDA/11/25/01/NP/MNR | RR/RDA/11/25/01 | Mahilankulam Pallamadhu road | Mannar | Mannar | George Steuart Engineering (Pvt)Ltd | 50% | 189602588.3 | 274228723.54 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-26 | 2026-05-25
RR/RDA/11/25/02/NP/MNR | RR/RDA/11/25/02 | Piramanayankulam Parappukadanthan road | Mannar | Mannar | George Steuart Engineering (Pvt)Ltd | 55% | 169538631.82 | 244135763.06 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-26 | 2026-05-25
RR/RDA/11/25/04/NP/MNR | RR/RDA/11/25/04 | Tharavankottai to Keeri Main Road | Mannar | Mannar | VN Construction JV | 60% | 146489579.5 | 76333504.2 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-04 | 2026-06-04
RR/RDA/11/25/07/NP/MNR | RR/RDA/11/25/07 | Avithappar Panimayam Internal Road with Culvert - Pesalai | Mannar | Mannar | VN Construction JV | 70% | 0 | 85087335.02 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-04 | 2026-06-04
RR/RDA/11/25/11/NP/MNR | RR/RDA/11/25/11 | Eruvittan - Vellalakaddu Road | Mannar | Mannar | VN Construction JV | 5% | 0 | 57826727.83 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-04 | 2026-06-04
RR/RDA/11/25/05/NP/MNR | RR/RDA/11/25/05 | Konnayan Kudiyiruppu Internal Main Road | Mannar | Mannar | Sun Constructions (Pvt) Ltd. | 5% | 90000000 | 135947165.98 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-08 | 2026-05-09
RR/RDA/11/25/09/NP/MNR | RR/RDA/11/25/09 | Renovation of Mathirikiramam internal Road Naruvilikulam | Mannar | Mannar | Abdul Cader Constructions | 70% | 28422878 | 40820067.58 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-17 | 2026-03-11
RR/RDA/11/25/16/NP/MNR | RR/RDA/11/25/16 | P.P.Potkerny Scheme Internal Road 1 | Mannar | Mannar | Abdul Cader Constructions | 70% | 14295963 | 20672459.81 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-02
RR/RDA/11/25/18/NP/MNR | RR/RDA/11/25/18 | Akaththimurippu Internal Road 3 | Mannar | Mannar | Abdul Cader Constructions | 70% | 15815393 | 23278986.71 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-02
RR/RDA/14/25/06/NP/KLN | RR/RDA/14/25/06 | Skanthapuram Kannan Temple road | Kilinochchi | Kilinochchi | Sun Constructions (Pvt) Ltd. | 35% | 138750000 | 214117844.07 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-03 | 2026-03-03
RR/RDA/14/25/08/NP/KLN | RR/RDA/14/25/08 | Kalmadu 7th unit 3rd lane | Kilinochchi | Kilinochchi | Kanola Constructions & Engineering (Pvt) Ltd | 20% | 58116410 | 92284361.31 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-03 | 2026-03-03
RR/RDA/14/25/09/NP/KLN | RR/RDA/14/25/09 | Neliyai Amman kovil road | Kilinochchi | Kilinochchi | Kanola Constructions & Engineering (Pvt) Ltd | 0% | 113238042.5 | 182796432.72 | Awarded | Tender Above 50Mn |  |  |  | 2025-12-10 | 2026-03-10
RR/RDA/10/25/24/NP/KLN | RR/RDA/10/25/24 | Kevil Nithtiyaveddai Road 2.150 | Kilinochchi | Kilinochchi | Kanola Constructions & Engineering (Pvt) Ltd | 0% | 67998480 | 112111761.11 | Awarded | Tender Above 50Mn |  |  |  | 2025-12-10 | 2026-03-10