## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/01/25/14/WP/COL | RR/RDA/01/25/14 | Development of the section from Arangala Bridge to Mihindu Mawatha in Malabe West Division | Colombo | Colombo | W.A. Perera & Company (Pvt) Ltd. | 68% | 33591596.5 | 51359519.36 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-10 | 2026-05-12
RR/RDA/01/25/19WP/COL | RR/RDA/01/25/19 | Puwakpitiya Dharmalapala Mawatha Main Road Development of the road from High Level Road to Elstonwatte Volleyball Court | Colombo | Avissawella | Asela Construction | 90% | 9189060 | 11872168.81 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-13 | 2026-05-15
RR/RDA/01/25/26/WP/COL | RR/RDA/01/25/26 | Boraluwathenna Pahala Uda Road | Colombo | Avissawella | Next Engineering Services (PVT) LTD | 5% | 21870721.4 | 27759276.9 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-28 | 2026-05-29
RR/RDA/01/25/30/WP/COL | RR/RDA/01/25/30 | Development of the road from near the transformer near Seebara Kade, Boralugoda to the Jayanthi Road | Colombo | Colombo | Asset Engineering (Pvt)LTD | 0% | 21619184.95 | 22641802.22 | Awarded | Tender Below 50Mn |  |  |  | 2026-07-30 | 2026-08-29
RR/RDA/02/25/03/WP/GMP | RR/RDA/02/25/03 | Development of De silva road beginning from Angurukaramulla temble road to Negombo Colombo road | Gampaha | Negombo | Dilini Builders (PVT) LTD | 0% | 5430100 | 6886574.13 | Awarded | Tender Below 50Mn |  |  |  | 2026-06-29 | 2026-09-28
RR/RDA/02/25/08 | RR/RDA/02/25/08 | Carpeting of the road from near the Buddha Temple towards the Lindara Temple on the Neligama Guru Godella Road started from Halugama Dharmapala Colledge in the Lindara Grama Niladhari Division of the Mirigama Divisional Secretariat. | Gampaha | Nittambuwa | Wijerathna Construction | 20% | 44980000 | 69742766.87 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-07 | 2026-06-05
| RR/RDA/02/25/10 | The road from Thaladuwa Road near Negombo Bus Stand, passing Jude Church, to the cemetery | Gampaha | Negombo | Dilini Builders (PVT) LTD | 0% | 35997890 | 43987022.27 | Awarded | Tender Below 50Mn |  |  |  | 2026-05-13 | 2026-08-12
| RR/RDA/02/25/11 | Road from Pinnawatta Junction to Mr. Sandaruwan's shop on the Hapitiya entrance road | Gampaha | Nittambuwa | Jeyanthan Construction | 0% | 15498360 | 21828855.77 | Awarded | Tender Below 50Mn |  |  |  | 2026-04-21 | 2026-07-21
| RR/RDA/02/25/15 | Udupila South Dolewatta | Gampaha | Gampaha | Creates Consultant and Construction | 0% | 7423117.7 | 8968820.62 | Awarded | Tender Below 50Mn |  |  |  | 2026-04-15 | 2026-07-14
RR/RDA/02/25/18/WP/GAM | RR/RDA/02/25/18 | Peliyagoda Naranminiya Road | Gampaha | Gampaha | Ceylux Civil engineering (Pvt) Ltd | 0% | 19082810 | 24821169.03 | Awarded | Tender Below 50Mn |  |  |  | 2026-07-26 | 2026-10-20
| RR/RDA/02/25/19 | 3 A road carpeted development near the Japanese Montessori at the junction of the North Kadirana Division. | Gampaha | Negombo | Jeyanthan Construction | 0% | 15141484.5 | 21486157.55 | Awarded | Tender Below 50Mn |  |  |  | 2026-04-21 | 2026-07-21
| RR/RDA/02/25/22 | 241 B Near Weliweriya North Suruwama Junction to Weliweriya Town | Gampaha | Gampaha | Yagoda Construction | 0% | 11473274.8 | 12991931.82 | Awarded | Tender Below 50Mn |  |  |  | 2026-07-29 | 2026-10-29
| RR/RDA/02/25/24 | Near Urapana Sisira Coir Mill to Hapugahagama Co-operative | Gampaha | Negombo | Jeyanthan Construction | 0% | 19032750 | 26884145.14 | Awarded | Tender Below 50Mn |  |  |  | 2026-04-10 | 2026-07-10
RR/RDA/03/25/12/WP/KTR | RR/RDA/03/25/12 | Concreting Batawala Road | Kalutara | Horana | Next Engineering Services (PVT) LTD | 39% | 18670236.2 | 26342506.07 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-22 | 2026-04-21
RR/RDA/03/25/16/WP/KTR | RR/RDA/03/25/16 | Development of carpeting of 1 km from Gane Aramba Road, Bogalla Junction to Ambepitiya Pinhena | Kalutara | Kalutara | Asela Construction | 0% | 27990360 | 37805645.98 | Awarded | Tender Below 50Mn |  |  |  | 2026-04-03 | 2026-07-03
| RR/RDA/03/25/17 | Development of 0.8 km carpeting of Newfa Mawatha | Kalutara | Kalutara | Develco Engineering (PVT) LTD | 0% | 6972603.95 | 8350944.75 | Awarded | Tender Below 50Mn |  |  |  | 2026-04-22 | 2026-07-22
RR/RDA/03/25/18/WP/KTR | RR/RDA/03/25/18 | Development of carpeting of the section (length 800 m) from near Minerithenna temple to Jananandanarama temple | Kalutara | Kalutara | Asela Construction | 0% | 17101775 | 23076319.79 | Awarded | Tender Below 50Mn |  |  |  | 2026-04-03 | 2026-07-03
| RR/RDA/03/25/19 | Carpeting and development of 500 meters of Moragahakanda watta Bodumaga Senasuna Viharastha Road | Kalutara | Kalutara | Develco Engineering (PVT) LTD | 55% | 8285619 | 9421190.92 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-04-22 | 2026-07-22
| RR/RDA/03/25/21 | Development of from Lewis Stadium to Heladiva Malshalawa | Kalutara | Kalutara | Develco Engineering (PVT) LTD | 55% | 15591781.1 | 18421245.76 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-04-22 | 2026-07-22