## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/16/25/03/AKK/AMP | RR/RDA/16/25/03 | Polbedda Junction to Galwalayaya Road | Ampara | Dehiaattakandiya | MOTEC Engineering & Construction | 52% | 17506335 | 24800970.39 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-10 | 2026-03-10 | 2026-03-16
RR/RDA/SP/16/25/01/AKK/AMP | RR/RDA/SP/16/25/01 | Rectification and Asphalt Surfacing on Ambahagawela -Namaloya Main Road | Ampara | Ampara | SMA Careem Engineering Consultancy Services & Suppliers (Pvt) Ltd | 34% | 222189859.13 | 306475548.92 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-31 | 2026-06-30
RR/RDA/STA II/16/25/03/AKK/AMP | RR/RDA/STA II/16/25/03 | Padiyathalawa Navinna road from Navinna Junction A5 to Navinna Bridge | Ampara | Dehiaattakandiya | Vithu Construction | 65% | 39470000 | 60426139.14 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-25 | 2026-05-26
RR/RDA/16/25/10KM/01/AKK/AMP | RR/RDA/16/25/10KM/01 | The road from the bridge near Ridee ela Temple to Island Plot No. 197 | Ampara | Dehiaattakandiya | Sawsiri Construction | 17% | 24113338.37 | 34027781.43 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-25 | 2026-05-26
RR/RDA/16/25/10KM/02/AKK/AMP | RR/RDA/16/25/10KM/02 | Road from Nelum Cafe Junction to Neeththa | Ampara | Ampara | Gama Construction & Consultant pvt Ltd | 20% | 19318560.1 | 29760217.62 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-07 | 2026-06-05
RR/RDA/16/25/10KM/03/AKK/AMP | RR/RDA/16/25/10KM/03 | On the road from Pulungasmulla to Padawala, the road from near Shanta Veladasala towards Padawala | Ampara | Dehiaattakandiya | Sawsiri Construction | 55% | 21202726.44 | 32963348.47 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-24 | 2026-05-25
RR/RDA/16/25/10KM/04/AKK/AMP | RR/RDA/16/25/10KM/04 | Vevinna Boogas Junction Inner Road | Ampara | Ampara | Gama Construction & Consultant pvt Ltd | 15% | 9692957.45 | 14460000 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-07 | 2026-05-08
RR/RDA/16/25/10KM/05/AKK/AMP | RR/RDA/16/25/10KM/05 | Road from Dorapaha Junction to Navagiriya Lake | Ampara | Ampara | Ema Constructions (Pvt) Ltd | 10% | 18058942 | 28554939.58 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-09 | 2026-06-07
RR/RDA/16/25/10KM/07/AKK/AMP | RR/RDA/16/25/10KM/07 | Bedirakka Malgastalawa Road | Ampara | Dehiaattakandiya | Pearl Construction | 0% | 16362791.5 | 28483156.49 | Awarded | Tender Below 50Mn |  |  |  | 2026-03-14 | 2026-05-15
RR/RDA/16/25/10KM/08/AKK/AKK | RR/RDA/16/25/10KM/08 | RDS Road Addalachena 6, 8 | Ampara | Akkaraipattu | MLH & sons Construction | 0% | 18326682.5 | 29731841.59 | Awarded | Tender Below 50Mn |  |  |  | 2026-02-26 | 2026-05-27
RR/RDA/16/25/10KM/11/AKK/AKK | RR/RDA/16/25/10KM/11 | Kalyana Road - Periyanilavanai Vishnu Kovil Road to Maradamuna Mashur Maulana Road | Ampara | Kalmunai | Zaka Engineering Consultancy | 10% | 20596083.2 | 32835450.73 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-08 | 2026-06-06
RR/RDA/16/25/10KM/13/AKK/AKK | RR/RDA/16/25/10KM/13 | Jaica - Tsunami Village Road | Ampara | Akkaraipattu | Gama Construction & Consultant pvt Ltd | 70% | 26167747.32 | 39951889.78 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-15 | 2026-06-13