## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/20/25/10/NCP/ANP | RR/RDA/20/25/10 | Manewe sita machchiyagama dakwa margaya | Anuradhapura | Maradankadawala | Sawsiri Construction | 100% | 31702147.54 | 39026908.38 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-28 | 2026-01-20
RR/RDA/20/25/13/NCP/ANP | RR/RDA/20/25/13 | Maradankadawala Habarana pare kaudawa handiyen patangena rambewa gammanaya dakwa margaya | Anuradhapura | Maradankadawala | Sawsiri Construction | 100% | 21609366.35 | 26367721.95 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-28 | 2026-01-20
RR/RDA/20/25/16/NCP/ANP | RR/RDA/20/25/16 | Hiriwadunna handiye sita idigaswewa pansal handiya dakwa margaya | Anuradhapura | Maradankadawala | Sun Constructions (Pvt) Ltd. | 80% | 33000000 | 59684748.55 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-03 | 2026-03-04 | 2026-05-25
RR/RDA/20/25/29/NCP/ANP | RR/RDA/20/25/29 | Development of the road from Udugama Colony rural road near the A9 road to the front of Mr. Somaratne Senanayake's house | Anuradhapura | Maradankadawala | Priyantha Civil Engineering | 0% | 27986392.06 | 32982943.17 | Awarded | Tender Below 50Mn |  |  |  | 2026-08-10 | 2026-11-02
RR/RDA/20/25/15 |  | Dikediyaya mahaweli pradhana ele sita galewela pradhana margaya | Anuradhapura | Maradankadawala |  | 100% | 36922235.4 | 36922235.4 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-10-19
RR/RDA/20/25/08 |  | Jaya mawatha sita Kaththaragama pansala dakwa margaya | Anuradhapura | Maradankadawala |  | 100% | 15557589.26 | 15557589.26 | Awarded | DL Stage 02 | Yes | Yes | Yes |  |  | 2026-03-21