## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/22/25/07/UP/BDL | RR/RDA/22/25/07 | Tharuna Govipola Margaye ithiri Kotasa Sanwardanaya Kirieema | Badulla | Bandarawela | Samadhi Construction | 0% | 13290035.01 | 15552666.77 | Awarded | Tender Below 50Mn |  |  |  | 2025-11-14 | 2026-02-13
RR/RDA/22/25/08/UP/BDL | RR/RDA/22/25/08 | Maragaha ella Margaya Concrete Kireema | Badulla | Bandarawela | Priyantha Rathnayaka | 100% | 5650802.3 | 9166668.15 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-11 | 2026-02-10
RR/RDA/22/25/09/UP/BDL | RR/RDA/22/25/09 | Piyarapandowa Neluwa Margaya | Badulla | Bandarawela | Liyanage Contractors | 10% | 38470000 | 54647573.75 | Awarded | Tender Above 50Mn | Yes | Yes | Yes
RR/RDA/22/26/01 |  | Rajamawatha Road | Badulla | Bandarawela |  | 100% | 15077652.84 | 15077652.84 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-25
RR/RDA/22/25/10 |  | Kosgolla Edaru Ulpatha Margaya | Badulla | Bandarawela |  | 100% | 13085885.7 | 13085885.7 | Awarded | DL Stage 02 | Yes | Yes | Yes |  | 2025-10-30 | 2025-11-20