## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/01/25/09/WP/COL | RR/RDA/01/25/09 | Kottawa Malabe Road Sirimalwatta 1 Main road carpeted and developed | Colombo | Avissawella | Accon Engineering (PVT) LTD | 100% | 2424881.23 | 2804484.03 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-30 | 2025-12-14 | 2025-11-30
RR/RDA/01/25/19WP/COL | RR/RDA/01/25/19 | Puwakpitiya Dharmalapala Mawatha Main Road Development of the road from High Level Road to Elstonwatte Volleyball Court | Colombo | Avissawella | Asela Construction | 90% | 9189060 | 11872168.81 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-13 | 2026-05-15
RR/RDA/01/25/26/WP/COL | RR/RDA/01/25/26 | Boraluwathenna Pahala Uda Road | Colombo | Avissawella | Next Engineering Services (PVT) LTD | 5% | 21870721.4 | 27759276.9 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-28 | 2026-05-29
RR/RDA/01/25/07 |  | 428/B Ihala Kosgama Grama Niladhari Wasame Praja Shalawa Pahala Margaya | Colombo | Avissawella |  | 100% | 51557606.95 | 51557606.95 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-10-17
RR/RDA/01/25/06 |  | Development of Rambutan gahamula Suramya Mawatha using carpet in Magammana East Grama Niladhari Domain | Colombo | Avissawella |  | 100% | 16341118.27 | 16341118.27 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-11-07 | 2025-11-15
RR/RDA/01/25/17 |  | Access road to Polgasowita Dikhena Aranya | Colombo | Avissawella |  | 100% | 7965231.1 | 7965231.1 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-26 | 2025-11-15 | 2025-11-15
RR/RDA/01/26/10KM/01 |  | Development of Honnatthara South Kudamadhuwa Road, Moonamalgahawatte Road up to House No. 138/3 by laying carpet and installing drains. | Colombo | Avissawella |  | 5% | 20626056.18 | 20626056.18 | Awarded | DL Stage 04 | Yes | Yes | Yes