## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/07/25/02/SP/GAL | RR/RDA/07/25/02 | Delgahabedda-Kirimatiya Margaya | Galle | Galle | Dissanayaka Builders | 93% | 26404581.16 | 50069275.91 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2025-12-31
RR/RDA/07/25/05/SP/GAL | RR/RDA/07/25/05 | Atawalawatta Sri Rewatha Viduhala Idiripita Margaya | Galle | Galle | Dissanayaka Builders | 95% | 25809376.97 | 45727567.86 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-01-28
RR/RDA/07/25/06/SP/GAL | RR/RDA/07/25/06 | Mulana Nagenahira ha Panwila Grama Niladari Wasam Sambandha wana athuru Margaya | Galle | Galle | Star Light Construction | 100% | 13805759 | 22862917.58 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2025-12-06
RR/RDA/07/25/11/SP/GAL | RR/RDA/07/25/11 | Elathota Pituwara Margaya Depasa Kanu ha Pathi Bami Yoda Carpet Kirima | Galle | Galle | Jayathissa Construction | 100% | 20801618.2 | 32148979.96 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2025-12-29
RR/RDA/07/25/12/SP/GAL | RR/RDA/07/25/12 | Galandeniya Margaya | Galle | Galle | Star Light Construction | 100% | 26433958.63 | 44471797.26 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-01-30
RR/RDA/07/25/13/SP/GAL | RR/RDA/07/25/13 | Aganaketiya Anuruddagama Mansandiye sita Samagipura dakwa Pradana Maragaya | Galle | Galle | EHL Constructions | 0% | 66310000 | 73974599.04 | Awarded | Tender Above 50Mn
RR/RDA/07/25/17/SP/GAL | RR/RDA/07/25/17 | Dasa Kadaya Asala sita Jack Fruit Ceylon (Pvt) ayathanaya dakwa Margaya 1 Km carpert kirima | Galle | Galle | P.H. Engineering Construction (Pvt) Ltd | 47% | 20798250 | 33516218.38 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-01-30
RR/RDA/07/25/19/SP/GAL | RR/RDA/07/25/19 | SuriEla Margaya | Galle | Galle | A.D. Herath Engineering | 96% | 14387747 | 18573267.25 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-09 | 2026-01-08 | 2026-02-27
RR/RDA/07/26/10KM/14 | RR/RDA/07/26/10KM/14 | Kodagoda Thudugala Road | Galle | Galle | Jayathissa Construction | 0% | 43914369.51 | 49447887.76 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-18 | 2026-12-18
RR/RDA/07/26/10KM/18 | RR/RDA/07/26/10KM/18 | Expansion of Alikehena Road from Thalawa Junior College to Atakohota border | Galle | Galle | S.A.Construction | 0% | 32247273.3 | 34701241.47 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-24 | 2026-12-24
RR/RDA/07/26/10KM/20 | RR/RDA/07/26/10KM/20 | Development of Paramount City Road. | Galle | Galle | EHL Constructions | 0% | 17088929 | 21005952.76 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-21 | 2026-12-21
RR/RDA/07/26/10KM/21 | RR/RDA/07/26/10KM/21 | Concretisation of Dikhena Welamedda road up to Addunkelle with 2 culverts and side walls on both sides. | Galle | Galle | Isula Construction | 0% | 37684669 | 44235916.42 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-21 | 2026-12-21
RR/RDA/07/25/07 |  | Hapugala batuwanthuda Margaya Pivisume sita Roswudwatta Margaye Kelawara Dakwa Margaya (Jala Tankiya Margaya) | Galle | Galle |  | 100% | 27520890.73 | 27520890.33 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-22
RR/RDA/07/25/03 |  | Wackwella Palama asala sita aranbe handiya dakwa Margaya | Galle | Galle |  | 100% | 26781909.97 | 26781909.97 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-09-15
RR/RDA/07/25/04 |  | Galwehera C.P. the Silva Mawatha Carpet kirima | Galle | Galle |  | 100% | 30571235.08 | 30571235.09 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-10-30
RR/RDA/07/25/14 |  | Moonugoda Road | Galle | Galle |  | 100% | 21211506.6 | 21211506.6 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 | 2025-11-16
RR/RDA/07/25/22 |  | Asphalting Meepawala henegewaththa road | Galle | Galle |  | 100% | 21395564.1 | 21395564.1 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2025-11-19 | 2026-02-27 | 2026-02-28
RR/RDA/07/25/01 |  | Keselgahahena Pradana Margaya (Kanu Paddathiya Bokku Samaga) | Galle | Galle |  | 98% | 76680545.16 | 76680545.16 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 |  | 2026-03-31