## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/07/25/06/SP/GAL | RR/RDA/07/25/06 | Mulana Nagenahira ha Panwila Grama Niladari Wasam Sambandha wana athuru Margaya | Galle | Galle | Star Light Construction | 100% | 13805759 | 22862917.58 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2025-12-06
RR/RDA/07/25/08/SP/GAL | RR/RDA/07/25/08 | Mahajana Mawatha Magurukaduwa Margaya Elpitiya Pitigala Pradhana Margaye sita Magurukaduwa Awasanaya dakwa Concrete athura Sanwardanaya Kirima | Galle | Hiniduma | EHL Constructions | 100% | 27637049 | 39100160.8 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-17 | 2026-01-16 | 2026-02-09
RR/RDA/07/25/11/SP/GAL | RR/RDA/07/25/11 | Elathota Pituwara Margaya Depasa Kanu ha Pathi Bami Yoda Carpet Kirima | Galle | Galle | Jayathissa Construction | 100% | 20801618.2 | 32148979.96 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2025-12-29
RR/RDA/07/25/12/SP/GAL | RR/RDA/07/25/12 | Galandeniya Margaya | Galle | Galle | Star Light Construction | 100% | 26433958.63 | 44471797.26 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-01-30
RR/RDA/07/25/15/SP/GAL | RR/RDA/07/25/15 | Dikhena Margaya | Galle | Hiniduma | Thilak Kumara Builders | 100% | 34817376.22 | 51022213.05 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-01-30
RR/RDA/07/25/20/SP/GAL | RR/RDA/07/25/20 | Road from Kammale Kadaya Junction to Udumalagala Juunction | Galle | Hiniduma | Kumarage Enterprises(Pvt)Ltd | 100% | 25272045.84 | 40743279.23 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-09 | 2026-01-30
RR/RDA/07/25/07 |  | Hapugala batuwanthuda Margaya Pivisume sita Roswudwatta Margaye Kelawara Dakwa Margaya (Jala Tankiya Margaya) | Galle | Galle |  | 100% | 27520890.73 | 27520890.33 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-22
RR/RDA/07/25/16 |  | Mahabodhiwatta sita Pongiliya haraha Vitahna Gedera Ela Dakwa Margaya Ketapathaliya Bokkuwa Athuluwa Bokku Sanwardanaya kara Concrete Kirima | Galle | Hiniduma |  | 100% | 30597079.78 | 30597079.78 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-31
RR/RDA/07/25/03 |  | Wackwella Palama asala sita aranbe handiya dakwa Margaya | Galle | Galle |  | 100% | 26781909.97 | 26781909.97 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-09-15
RR/RDA/07/25/04 |  | Galwehera C.P. the Silva Mawatha Carpet kirima | Galle | Galle |  | 100% | 30571235.08 | 30571235.09 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-10-30
RR/RDA/07/25/18 |  | Agaliya Uthura Tranformaraya Sita Savanna Wella desata Margaya Interlock Kirima | Galle | Hiniduma |  | 100% | 27525465.5 | 27525465.5 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-10-30
RR/RDA/07/25/14 |  | Moonugoda Road | Galle | Galle |  | 100% | 21211506.6 | 21211506.6 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 | 2025-11-16
RR/RDA/07/25/22 |  | Asphalting Meepawala henegewaththa road | Galle | Galle |  | 100% | 21395564.1 | 21395564.1 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2025-11-19 | 2026-02-27 | 2026-02-28
RR/RDA/07/25/21 |  | Asphalting Newungala Na tree to Bedimeda road | Galle | Hiniduma |  | 100% | 35369824.16 | 35369824.16 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2025-11-18 | 2026-03-20 | 2026-02-15
RR/RDA/07/25/01 |  | Keselgahahena Pradana Margaya (Kanu Paddathiya Bokku Samaga) | Galle | Galle |  | 98% | 76680545.16 | 76680545.16 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 |  | 2026-03-31