## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/02/25/08 | RR/RDA/02/25/08 | Carpeting of the road from near the Buddha Temple towards the Lindara Temple on the Neligama Guru Godella Road started from Halugama Dharmapala Colledge in the Lindara Grama Niladhari Division of the Mirigama Divisional Secretariat. | Gampaha | Nittambuwa | Wijerathna Construction | 20% | 44980000 | 69742766.87 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-07 | 2026-06-05
| RR/RDA/02/25/11 | Road from Pinnawatta Junction to Mr. Sandaruwan's shop on the Hapitiya entrance road | Gampaha | Nittambuwa | Jeyanthan Construction | 0% | 15498360 | 21828855.77 | Awarded | Tender Below 50Mn |  |  |  | 2026-04-21 | 2026-07-21
RR/RDA/02/25/01 |  | Heendeniya Dumriya Sthanaya Dakwa Margaya | Gampaha | Nittambuwa |  | 100% | 13144147.11 | 13144147.11 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-07-09