## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/02/25/05/WP/GMP | RR/RDA/02/25/05 | Improvements to 70/A Pahala Kandawala Grama Niladharee wasame suuriya mawathe athuru mawathak wana jayashantha mahathaage niwasa asalin athi para praja shaalawa dakwaa saha dakunu pasata thi wiharasthanaya dakwa kotasa | Gampaha | Negombo | Jeyanthan Construction | 100% | 16250193.4 | 21560731.47 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-30 | 2026-01-29 | 2025-12-23
RR/RDA/02/25/03/WP/GMP | RR/RDA/02/25/03 | Development of De silva road beginning from Angurukaramulla temble road to Negombo Colombo road | Gampaha | Negombo | Dilini Builders (PVT) LTD | 0% | 5430100 | 6886574.13 | Awarded | Tender Below 50Mn |  |  |  | 2026-06-29 | 2026-09-28
RR/RDA/02/25/08 | RR/RDA/02/25/08 | Carpeting of the road from near the Buddha Temple towards the Lindara Temple on the Neligama Guru Godella Road started from Halugama Dharmapala Colledge in the Lindara Grama Niladhari Division of the Mirigama Divisional Secretariat. | Gampaha | Nittambuwa | Wijerathna Construction | 20% | 44980000 | 69742766.87 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-07 | 2026-06-05
| RR/RDA/02/25/10 | The road from Thaladuwa Road near Negombo Bus Stand, passing Jude Church, to the cemetery | Gampaha | Negombo | Dilini Builders (PVT) LTD | 0% | 35997890 | 43987022.27 | Awarded | Tender Below 50Mn |  |  |  | 2026-05-13 | 2026-08-12
| RR/RDA/02/25/11 | Road from Pinnawatta Junction to Mr. Sandaruwan's shop on the Hapitiya entrance road | Gampaha | Nittambuwa | Jeyanthan Construction | 0% | 15498360 | 21828855.77 | Awarded | Tender Below 50Mn |  |  |  | 2026-04-21 | 2026-07-21
| RR/RDA/02/25/15 | Udupila South Dolewatta | Gampaha | Gampaha | Creates Consultant and Construction | 0% | 7423117.7 | 8968820.62 | Awarded | Tender Below 50Mn |  |  |  | 2026-04-15 | 2026-07-14
RR/RDA/02/25/18/WP/GAM | RR/RDA/02/25/18 | Peliyagoda Naranminiya Road | Gampaha | Gampaha | Ceylux Civil engineering (Pvt) Ltd | 0% | 19082810 | 24821169.03 | Awarded | Tender Below 50Mn |  |  |  | 2026-07-26 | 2026-10-20
| RR/RDA/02/25/19 | 3 A road carpeted development near the Japanese Montessori at the junction of the North Kadirana Division. | Gampaha | Negombo | Jeyanthan Construction | 0% | 15141484.5 | 21486157.55 | Awarded | Tender Below 50Mn |  |  |  | 2026-04-21 | 2026-07-21
| RR/RDA/02/25/22 | 241 B Near Weliweriya North Suruwama Junction to Weliweriya Town | Gampaha | Gampaha | Yagoda Construction | 0% | 11473274.8 | 12991931.82 | Awarded | Tender Below 50Mn |  |  |  | 2026-07-29 | 2026-10-29
| RR/RDA/02/25/24 | Near Urapana Sisira Coir Mill to Hapugahagama Co-operative | Gampaha | Negombo | Jeyanthan Construction | 0% | 19032750 | 26884145.14 | Awarded | Tender Below 50Mn |  |  |  | 2026-04-10 | 2026-07-10
RR/RDA/02/25/02 |  | Development from the road in front of Kanti Teacher's house onwards to Vivekarama Temple (up to Uruwal Mawatha). | Gampaha | Gampaha |  | 100% | 10523274.77 | 10523274.77 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-15
RR/RDA/02/25/01 |  | Heendeniya Dumriya Sthanaya Dakwa Margaya | Gampaha | Nittambuwa |  | 100% | 13144147.11 | 13144147.11 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-07-09
RR/RDA/02/25/04 |  | Delpe Kadawara sita Nelumwaththa margaya arambaye sita Dewadasa mahathage niwasa dakwa Margaya | Gampaha | Negombo |  | 100% | 26006255.54 | 26006255.54 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-10
RR/RDA/02/25/07 |  | Road near Ozon Educational Institiute | Gampaha | Gampaha |  | 100% | 12058540.61 | 12058540.61 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-10-27 |  | 2025-11-05
RR/RDA/02/25/20 |  | St. Lazarus Road (Depot Road) | Gampaha | Negombo |  | 100% | 26943025.76 | 23521864.99 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 |  | 2026-03-31