## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/08/25/Si |  | Sithulpauwa Rajamaha Viharaye Katharagama Para | Hambantota | Hambantota |  | 100% | 3969390.34 | 3969390.34 | Awarded | DL Stage 01 | Yes | Yes | Yes |  | 2025-08-15
RR/RDA/08/25/04 |  | Vigamuwa Pattiyapola Road from Vigamuwa School | Hambantota | Tangalle |  | 100% | 74802039.66 | 74802039.66 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-15
RR/RDA/09/25/01 |  | Karametiya Road | Hambantota | Hambantota |  | 100% | 74446690.12 | 74446690.12 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-15
RR/RDA/09/25/02 |  | Wam Iwura Janawasa Margaya | Hambantota | Hambantota |  | 100% | 37666563.49 | 37666563.49 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-10-30 | 2025-10-25
RR/RDA/09/25/12 |  | Development of the road from Lunugamwehera Jadura Lake to Udaeva | Hambantota | Hambantota |  | 92% | 66506406.57 | 66506406.57 | Awarded | DL Stage 04 | Yes | Yes | Yes |  |  | 2026-03-31
RR/RDA/09/25/06 |  | Raluwa main road | Hambantota | Tangalle |  | 70% | 17377865.99 | 17377865.99 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2025-12-01 |  | 2026-03-31
RR/RDA/09/25/14 |  | Development of road near Olu ara School | Hambantota | Tangalle |  | 90% | 101801692.33 | 101801692.33 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 |  | 2026-03-31
RR/RDA/09/25/10 |  | Development of Valasmulla Pallekanda road from 3 km post to 5 km post | Hambantota | Tangalle |  | 95% | 84525263.23 | 84525263.23 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-02-10 |  | 2026-03-31