## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/03/25/02/WP/KTR | RR/RDA/03/25/02 | Concreting of the first side road on the left side of Rasik Road | Kalutara | Kalutara | Develco Engineering (PVT) LTD | 100% | 7705537.2 | 11126896.75 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-30 | 2025-12-29
RR/RDA/03/25/03/WP/KTR | RR/RDA/03/25/03 | Carpeting of Uswatta Lane | Kalutara | Kalutara | Ramano Engineers | 100% | 6059612.5 | 7444801.7 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-30 | 2025-12-29
RR/RDA/03/25/05/WP/KTR | RR/RDA/03/25/05 | From near Mr. Abeywardena's house on the Yawita Kammalgoda road block stones and development (first phase) | Kalutara | Horana | Develco Engineering (PVT) LTD | 100% | 21827299.85 | 31800339.88 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-30 | 2026-01-29
RR/RDA/03/25/08/WP/KTR | RR/RDA/03/25/08 | Asphalting from near Valkandala transformer to Panthiya Watta (Malamiriskanda road) | Kalutara | Agalawatta | Accon Engineering (PVT) LTD | 100% | 14577590.15 | 22843424.38 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-30 | 2026-01-29 | 2025-12-15
RR/RDA/03/25/09/WP/KTR | RR/RDA/03/25/09 | Concreting of Weedahena road | Kalutara | Agalawatta | Develco Engineering (PVT) LTD | 100% | 15010244 | 19919301.67 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-30 | 2026-01-29
RR/RDA/03/25/12/WP/KTR | RR/RDA/03/25/12 | Concreting Batawala Road | Kalutara | Horana | Next Engineering Services (PVT) LTD | 39% | 18670236.2 | 26342506.07 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-22 | 2026-04-21
| RR/RDA/03/25/19 | Carpeting and development of 500 meters of Moragahakanda watta Bodumaga Senasuna Viharastha Road | Kalutara | Kalutara | Develco Engineering (PVT) LTD | 55% | 8285619 | 9421190.92 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-04-22 | 2026-07-22
| RR/RDA/03/25/21 | Development of from Lewis Stadium to Heladiva Malshalawa | Kalutara | Kalutara | Develco Engineering (PVT) LTD | 55% | 15591781.1 | 18421245.76 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-04-22 | 2026-07-22
RR/RDA/03/25/01 |  | Asphalting Samagipura Road (LECO office to Maha ela) | Kalutara | Kalutara |  | 100% | 25713214.4 | 25713214.4 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/03/25/04 |  | Development of the Kotupathgoda road by asphalting | Kalutara | Horana |  | 100% | 32439574.76 | 32439574.76 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21 | 2025-11-15
RR/RDA/03/25/36 |  | 10 Mw T Jayarathne mahathge niwas asala concrete kara nawatha ati sthanaya sita nawa margaya desata | Kalutara | Agalawatta |  | 100% | 34917696.41 | 34917696.41 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/03/25/07 |  | Carpeting of Shekmadara Road | Kalutara | Kalutara |  | 100% | 14674228.65 | 14674228.65 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-07-14 | 2025-08-07
RR/RDA/03/25/11 |  | Jilani road in Darga Town | Kalutara | Kalutara |  | 100% | 14759196.13 | 14759196.13 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 | 2025-11-17 | 2025-11-25
RR/RDA/03/25/13 |  | Morapitiya Aluth Mawatha to 1st mile post via Rankoth lane | Kalutara | Agalawatta |  | 100% | 38713954.65 | 38713954.65 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 |  | 2026-02-28
RR/RDA/03/25/20 |  | Development of Gemunu Mawatha by laying 500 meters of carpet | Kalutara | Kalutara |  | 100% | 12547527.78 | 12547527.78 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 | 2026-03-12 | 2026-01-31