## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
| RR/RDA/SPE/14/25/01 | Pallavarayankaddu Junction - Kiranchi - Ponnaveli Road | Kilinochchi | Kilinochchi | Nimna Holdings (Pvt) Ltd | 0% | 206440000 | 237551577.31 | Awarded | Tender Above 50Mn
RR/RDA/14/25/06/NP/KLN | RR/RDA/14/25/06 | Skanthapuram Kannan Temple road | Kilinochchi | Kilinochchi | Sun Constructions (Pvt) Ltd. | 35% | 138750000 | 214117844.07 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-03 | 2026-03-03
RR/RDA/14/25/07/NP/KLN | RR/RDA/14/25/07 | Mayilvakanapuram kolunthupulavu road | Kilinochchi | Kilinochchi | RR Construction (Pvt) Ltd. | 30% | 224197154.05 | 353834298.91 | Awarded | Tender Above 50Mn | Yes | Yes | Yes
RR/RDA/14/25/08/NP/KLN | RR/RDA/14/25/08 | Kalmadu 7th unit 3rd lane | Kilinochchi | Kilinochchi | Kanola Constructions & Engineering (Pvt) Ltd | 20% | 58116410 | 92284361.31 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-03 | 2026-03-03
RR/RDA/14/25/09/NP/KLN | RR/RDA/14/25/09 | Neliyai Amman kovil road | Kilinochchi | Kilinochchi | Kanola Constructions & Engineering (Pvt) Ltd | 0% | 113238042.5 | 182796432.72 | Awarded | Tender Above 50Mn |  |  |  | 2025-12-10 | 2026-03-10
RR/RDA/10/25/24/NP/KLN | RR/RDA/10/25/24 | Kevil Nithtiyaveddai Road 2.150 | Kilinochchi | Kilinochchi | Kanola Constructions & Engineering (Pvt) Ltd | 0% | 67998480 | 112111761.11 | Awarded | Tender Above 50Mn |  |  |  | 2025-12-10 | 2026-03-10
RDA/GOSL/NP/RR/LCB/PACKAGE 1(KN) | NKL006 | Vannerikulam Jeyapuram Road, Anaikkaddy Road, Veddukkaddu Road Sec.i & iii and Sekkalai Mudkompan Road | Kilinochchi |  | RR Construction (Pvt) Ltd. | 0% | 801739984.32 | 758268144.22 | Awarded | PIU
RR/RDA/14/25/05 |  | Kanakapuram school behind road | Kilinochchi | Kilinochchi |  | 100% | 43582937.83 | 43582937.83 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-10-16 |  | 2026-03-31