## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/14/25/06/NP/KLN | RR/RDA/14/25/06 | Skanthapuram Kannan Temple road | Kilinochchi | Kilinochchi | Sun Constructions (Pvt) Ltd. | 35% | 138750000 | 214117844.07 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-03 | 2026-03-03
RR/RDA/14/25/07/NP/KLN | RR/RDA/14/25/07 | Mayilvakanapuram kolunthupulavu road | Kilinochchi | Kilinochchi | RR Construction (Pvt) Ltd. | 30% | 224197154.05 | 353834298.91 | Awarded | Tender Above 50Mn | Yes | Yes | Yes
RR/RDA/14/25/08/NP/KLN | RR/RDA/14/25/08 | Kalmadu 7th unit 3rd lane | Kilinochchi | Kilinochchi | Kanola Constructions & Engineering (Pvt) Ltd | 20% | 58116410 | 92284361.31 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-03 | 2026-03-03
RR/RDA/14/25/05 |  | Kanakapuram school behind road | Kilinochchi | Kilinochchi |  | 100% | 43582937.83 | 43582937.83 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-10-16 |  | 2026-03-31