## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/18/25/11/NWP/KRG | RR/RDA/18/25/11 | Development of road from Dambulu Road to Havanathenna via Ehelagollaya | Kurunegala | Kurunegala | Shanho Enterprises Pvt Ltd. | 65% | 46193949.68 | 64750199.52 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-04 | 2026-07-01 | 2026-08-01
RR/RDA/18/25/104/NWP/KRG | RR/RDA/18/25/104 | Pinnagolla Junction to Kokowaththa Junction VIA Alakolapelessa | Kurunegala | Kurunegala | Senerath Engineering (pvt) Ltd | 100% | 24010872.6 | 30550483.75 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-21 | 2025-12-20 | 2025-12-20
RR/RDA/18/25/106/NWP/KRG | RR/RDA/18/25/106 | Thagahinna Temple Road | Kurunegala | Kurunegala | Jayawansa Construction (PVT) Ltd | 100% | 13370813.5 | 16225030.21 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2026-03-09 | 2025-12-15
RR/RDA/18/25/NWP/KRG/10 | RR/RDA/18/25/107 | Uyandana Yaggapitiya | Kurunegala | Kurunegala | Senerath Engineering (pvt) Ltd | 100% | 45801928.2 | 71428674.02 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-03-03 | 2026-05-07
RR/RDA/18/25/135/NWP/KRG | RR/RDA/18/25/135 | Kelegedara Gamameda Road (CTB Basaya Dawanaya wana) Kavudumunna, Kunumade, Hungan pitiya haraha diwena Margaya Kapat Kirima | Kurunegala | Kurunegala | Jayasinghe Contractors (Pvt) Ltd. | 20% | 41750386.7 | 55779764.12 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-20 | 2026-05-20 | 2026-05-20
RR/RDA/18/25/137/NWP/KRG | RR/RDA/18/25/137 | Damunugolla Sita Kobbewehera Handiya Dakwa Margaya Kapat Kirima | Kurunegala | Kurunegala | W P J Engineering(Pvt)Ltd | 45% | 18425029.46 | 23865719.81 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-07 | 2026-04-06 | 2026-06-06
RR/RDA/18/25/138/NWP/KRG | RR/RDA/18/25/138 | Pudukkulama Bogas Handiye sita Keppitiya haraha Thihawa Dakwa Margaya Kapat Kirima | Kurunegala | Kurunegala | W P J Engineering(Pvt)Ltd | 20% | 30650394.06 | 39359193.23 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-07 | 2026-04-07 | 2026-06-07
RR/RDA/18/25/139/NWP/KRG | RR/RDA/18/25/139 | Akkara Panaha Mansandiye Sita Walahamulla Dakwa Margaya | Kurunegala | Kurunegala | Jayawansa Construction (PVT) Ltd | 90% | 28112995.75 | 41102824.35 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-17 | 2026-05-18 | 2026-06-18
RR/RDA/18/25/12 |  | Anura Mahaththayalage niwase sita Nalalida dakwa kadurugaha ela dakwa margaya (Ganewatte) | Kurunegala | Kurunegala |  | 100% | 23242484.2 | 23242484.2 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/18/25/21 |  | Wattakkawatta Road - Paving of Road (ABC Paving) from near Kelimune Pustalaya. | Kurunegala | Kurunegala |  | 100% | 39422351.32 | 39422351.32 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-07 | 2025-09-10
RR/RDA/18/25/103 |  | Wellawa Thalatuwa Junction to Gepellawa Road | Kurunegala | Kurunegala |  | 100% | 31387050.89 | 31387050.89 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-04 | 2025-09-30
RR/RDA/18/25/105 |  | Thihawa Junction to Mailamada | Kurunegala | Kurunegala |  | 100% | 33866057.61 | 33866057.61 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-07 |  | 2025-10-31
RR/RDA/18/25/314 |  | Road from Nugawela Junction in Walagane to Maspotha Crematorium via Temple | Kurunegala | Kurunegala |  | 100% | 41562875.57 | 41562875.57 | Awarded | DL Stage 04 | Yes | Yes | Yes |  |  | 2026-02-28
RR/RDA/18/25/317 |  | Lakee Land Road in Wilattawa Division | Kurunegala | Kurunegala |  | 100% | 9799762.91 | 9799762.91 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-02-16 |  | 2026-03-31
RR/RDA/18/25/319 |  | Kabaledevgama 3rd Lane and 4 Lane in Kaballewa Division of Kaballewa Division | Kurunegala | Kurunegala |  | 100% | 21709247.87 | 21709247.87 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-26 |  | 2026-03-31