## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/18/25/01/NWP/KRG | RR/RDA/18/25/01 | Development of Egodagama Talakolawewa road | Kurunegala | Maho | Sri Ram Constructions | 60% | 98323766.14 | 156184445.89 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-08 | 2026-05-06 | 2026-07-09
RR/RDA/18/25/02/NWP/KRG | RR/RDA/18/25/02 | Road from Parakumpura to Yaya 04 | Kurunegala | Maho | Ingress Engineering | 100% | 20126522.24 | 24748740.38 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-29 | 2026-02-04 | 2025-12-28
RR/RDA/18/25/04/NWP/KRG | RR/RDA/18/25/04 | The road from Hunugallewa road junction to Madadenigama Hunugallewa Mahamaruwa Beligahaya to Mee Oya bridge | Kurunegala | Maho | Shanho Enterprises Pvt Ltd. | 40% | 59066766.74 | 85865152.06 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-09 | 2026-06-09 | 2026-06-09
RR/RDA/18/25/07/NWP/KRG | RR/RDA/18/25/07 | Road from Moragolla Junction to Nabadewa Girilla Carpet Road via Kirinda | Kurunegala | Maho | Jayasinghe Constructions (Pvt) Ltd. | 75% | 59247280.29 | 79393864.19 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-09 | 2026-05-12 | 2026-06-12
RR/RDA/18/25/08/NWP/KRG | RR/RDA/18/25/08 | Paving of road from Nammuawa to Nagansole temple | Kurunegala | Maho | Omega Construction (Pvt) Ltd | 100% | 33899382 | 49176148.86 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-04 | 2026-03-07 | 2025-12-20
RR/RDA/18/25/09/NWP/KRG | RR/RDA/18/25/09 | Paving the road from Pahala Galapitiyagama to Tharanagolla Sports Ground | Kurunegala | Maho | Senerath Engineering (pvt) Ltd | 0% | 70405428.6 | 81982091.15 | Awarded | Tender Above 50Mn |  |  |  | 2025-12-03 | 2026-03-03 | 2026-03-03
RR/RDA/18/25/11/NWP/KRG | RR/RDA/18/25/11 | Development of road from Dambulu Road to Havanathenna via Ehelagollaya | Kurunegala | Kurunegala | Shanho Enterprises Pvt Ltd. | 65% | 46193949.68 | 64750199.52 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-04 | 2026-07-01 | 2026-08-01
RR/RDA/18/25/16/NWP/KRG | RR/RDA/18/25/16 | Development of concrete road from near Wadawa temple to the lake | Kurunegala | Kuliyapitiya | Jayawardana Constructions (Pvt) Ltd. | 100% | 25583393 | 31595236.77 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-15 | 2025-12-15
RR/RDA/18/25/22/NWP/KRG | RR/RDA/18/25/22 | Paving of culverts and sidewalls at the necessary places on the road from near Moragane Samiti Hall to Siyambalaweva via Galkadulla. | Kurunegala | Kuliyapitiya | Jayasinghe Constructions (Pvt) Ltd. | 65% | 67074479.55 | 77881819.09 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-03 | 2026-06-04 | 2026-07-04
RR/RDA/18/25/24/NWP/KRG | RR/RDA/18/25/24 | Paving and developing the road from Seelarathana Mawatha to Girana Junction | Kurunegala | Kuliyapitiya | Senerath Engineering (pvt) Ltd | 100% | 37201129.8 | 57963603.67 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-03 | 2026-03-05 | 2026-04-02
RR/RDA/18/25/104/NWP/KRG | RR/RDA/18/25/104 | Pinnagolla Junction to Kokowaththa Junction VIA Alakolapelessa | Kurunegala | Kurunegala | Senerath Engineering (pvt) Ltd | 100% | 24010872.6 | 30550483.75 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-21 | 2025-12-20 | 2025-12-20
RR/RDA/18/25/106/NWP/KRG | RR/RDA/18/25/106 | Thagahinna Temple Road | Kurunegala | Kurunegala | Jayawansa Construction (PVT) Ltd | 100% | 13370813.5 | 16225030.21 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2026-03-09 | 2025-12-15
RR/RDA/18/25/NWP/KRG/10 | RR/RDA/18/25/107 | Uyandana Yaggapitiya | Kurunegala | Kurunegala | Senerath Engineering (pvt) Ltd | 100% | 45801928.2 | 71428674.02 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-03-03 | 2026-05-07
RR/RDA/18/25/135/NWP/KRG | RR/RDA/18/25/135 | Kelegedara Gamameda Road (CTB Basaya Dawanaya wana) Kavudumunna, Kunumade, Hungan pitiya haraha diwena Margaya Kapat Kirima | Kurunegala | Kurunegala | Jayasinghe Contractors (Pvt) Ltd. | 20% | 41750386.7 | 55779764.12 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-20 | 2026-05-20 | 2026-05-20
RR/RDA/18/25/136/NWP/KRG | RR/RDA/18/25/136 | Ranasinghe Hotel Asalin Koralaya Waththe sita Panwala Kubura Dakwa Diwena Margaya Kapat Kirima | Kurunegala | Kuliyapitiya | Jayasinghe Contractors (Pvt) Ltd. | 100% | 21718130.5 | 22994794.21 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-07 | 2026-04-07 | 2026-04-07
RR/RDA/18/25/137/NWP/KRG | RR/RDA/18/25/137 | Damunugolla Sita Kobbewehera Handiya Dakwa Margaya Kapat Kirima | Kurunegala | Kurunegala | W P J Engineering(Pvt)Ltd | 45% | 18425029.46 | 23865719.81 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-07 | 2026-04-06 | 2026-06-06
RR/RDA/18/25/138/NWP/KRG | RR/RDA/18/25/138 | Pudukkulama Bogas Handiye sita Keppitiya haraha Thihawa Dakwa Margaya Kapat Kirima | Kurunegala | Kurunegala | W P J Engineering(Pvt)Ltd | 20% | 30650394.06 | 39359193.23 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-07 | 2026-04-07 | 2026-06-07
RR/RDA/18/25/139/NWP/KRG | RR/RDA/18/25/139 | Akkara Panaha Mansandiye Sita Walahamulla Dakwa Margaya | Kurunegala | Kurunegala | Jayawansa Construction (PVT) Ltd | 90% | 28112995.75 | 41102824.35 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-17 | 2026-05-18 | 2026-06-18
| RR/RDA/18/25/308 | Wijekoon Mawatha near Narammala Bus Stand and Hospital Mawatha from Peralaswella | Kurunegala | Kuliyapitiya | Thushara roofing (pvt) ltd | 65% | 10696008.28 | 11985499.69 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-05-04 | 2026-08-02
RR/RDA/18/25/12 |  | Anura Mahaththayalage niwase sita Nalalida dakwa kadurugaha ela dakwa margaya (Ganewatte) | Kurunegala | Kurunegala |  | 100% | 23242484.2 | 23242484.2 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/18/25/05 |  | 158 Digana Grama niladari wasame 3 patumaga (vawa dakwa) (Yapahuwa) | Kurunegala | Maho |  | 100% | 11774916.28 | 11443000 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/18/25/23 |  | Horagasagara Nawarathna handiye sita Ihala kadigamuwa handiya dakwa margaya (Bingiriya) | Kurunegala | Kuliyapitiya |  | 100% | 61588475.92 | 61588475.92 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-31
RR/RDA/18/25/99 |  | Rajanganaya reservoir to Parakumpura Junction (Left bank Road) | Kurunegala | Maho |  | 100% | 312810182.55 | 312810182.55 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 |  | 2026-02-28
RR/RDA/18/25/06 |  | Walaliya Piduruwellewa road to the middle of the village | Kurunegala | Maho |  | 100% | 19431074.96 | 19537451.95 | Awarded | DL Stage 02 | Yes | Yes | Yes
RR/RDA/18/25/17 |  | No. 245 from near Jeevan Lasantha's house no. 37 Development of the main road up to Mr. Nihal's house with five (5) side roads. | Kurunegala | Kuliyapitiya |  | 100% | 51911526.67 | 51911526.67 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-07 | 2025-10-30 | 2025-11-15
RR/RDA/18/25/21 |  | Wattakkawatta Road - Paving of Road (ABC Paving) from near Kelimune Pustalaya. | Kurunegala | Kurunegala |  | 100% | 39422351.32 | 39422351.32 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-07 | 2025-09-10
RR/RDA/18/25/103 |  | Wellawa Thalatuwa Junction to Gepellawa Road | Kurunegala | Kurunegala |  | 100% | 31387050.89 | 31387050.89 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-04 | 2025-09-30
RR/RDA/18/25/105 |  | Thihawa Junction to Mailamada | Kurunegala | Kurunegala |  | 100% | 33866057.61 | 33866057.61 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-07 |  | 2025-10-31
RR/RDA/18/25/314 |  | Road from Nugawela Junction in Walagane to Maspotha Crematorium via Temple | Kurunegala | Kurunegala |  | 100% | 41562875.57 | 41562875.57 | Awarded | DL Stage 04 | Yes | Yes | Yes |  |  | 2026-02-28
RR/RDA/18/25/309 |  | From near Kongaha in Waudagama on the Katupotha Waudagama Wanduressegama road near Potuwewa Cemetery. | Kurunegala | Maho |  | 87% | 45888080.58 | 45888080.58 | Awarded | DL Stage 04 | Yes | Yes | Yes |  |  | 2026-03-31
RR/RDA/18/25/317 |  | Lakee Land Road in Wilattawa Division | Kurunegala | Kurunegala |  | 100% | 9799762.91 | 9799762.91 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-02-16 |  | 2026-03-31
RR/RDA/18/25/319 |  | Kabaledevgama 3rd Lane and 4 Lane in Kaballewa Division of Kaballewa Division | Kurunegala | Kurunegala |  | 100% | 21709247.87 | 21709247.87 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-26 |  | 2026-03-31
RR/RDA/18/25/311 |  | Road from Kopihena Junction to Dangolla in Damunugala Division of Piduruwella Division | Kurunegala |  |  | 100% | 55494114.67 | 55494114.67 | Awarded | DL Stage 04 | Yes | Yes | Yes |  |  | 2026-04-10
RR/RDA/18/25/312 |  | Junction in front of Narampola Thoraya Muslim College to Budanapartiya Road via Narampola | Kurunegala |  |  | 100% | 43368925.99 | 43368925.99 | Awarded | DL Stage 04 | Yes | Yes | Yes |  |  | 2026-04-10