## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/18/25/01/NWP/KRG | RR/RDA/18/25/01 | Development of Egodagama Talakolawewa road | Kurunegala | Maho | Sri Ram Constructions | 60% | 98323766.14 | 156184445.89 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-08 | 2026-05-06 | 2026-07-09
RR/RDA/18/25/04/NWP/KRG | RR/RDA/18/25/04 | The road from Hunugallewa road junction to Madadenigama Hunugallewa Mahamaruwa Beligahaya to Mee Oya bridge | Kurunegala | Maho | Shanho Enterprises Pvt Ltd. | 40% | 59066766.74 | 85865152.06 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-09 | 2026-06-09 | 2026-06-09
RR/RDA/18/25/07/NWP/KRG | RR/RDA/18/25/07 | Road from Moragolla Junction to Nabadewa Girilla Carpet Road via Kirinda | Kurunegala | Maho | Jayasinghe Constructions (Pvt) Ltd. | 75% | 59247280.29 | 79393864.19 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-09 | 2026-05-12 | 2026-06-12
RR/RDA/18/25/09/NWP/KRG | RR/RDA/18/25/09 | Paving the road from Pahala Galapitiyagama to Tharanagolla Sports Ground | Kurunegala | Maho | Senerath Engineering (pvt) Ltd | 0% | 70405428.6 | 81982091.15 | Awarded | Tender Above 50Mn |  |  |  | 2025-12-03 | 2026-03-03 | 2026-03-03
RR/RDA/18/25/11/NWP/KRG | RR/RDA/18/25/11 | Development of road from Dambulu Road to Havanathenna via Ehelagollaya | Kurunegala | Kurunegala | Shanho Enterprises Pvt Ltd. | 65% | 46193949.68 | 64750199.52 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-04 | 2026-07-01 | 2026-08-01
RR/RDA/18/25/22/NWP/KRG | RR/RDA/18/25/22 | Paving of culverts and sidewalls at the necessary places on the road from near Moragane Samiti Hall to Siyambalaweva via Galkadulla. | Kurunegala | Kuliyapitiya | Jayasinghe Constructions (Pvt) Ltd. | 65% | 67074479.55 | 77881819.09 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-03 | 2026-06-04 | 2026-07-04
RR/RDA/18/25/137/NWP/KRG | RR/RDA/18/25/137 | Damunugolla Sita Kobbewehera Handiya Dakwa Margaya Kapat Kirima | Kurunegala | Kurunegala | W P J Engineering(Pvt)Ltd | 45% | 18425029.46 | 23865719.81 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-07 | 2026-04-06 | 2026-06-06
RR/RDA/18/25/138/NWP/KRG | RR/RDA/18/25/138 | Pudukkulama Bogas Handiye sita Keppitiya haraha Thihawa Dakwa Margaya Kapat Kirima | Kurunegala | Kurunegala | W P J Engineering(Pvt)Ltd | 20% | 30650394.06 | 39359193.23 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-07 | 2026-04-07 | 2026-06-07
| RR/RDA/18/25/308 | Wijekoon Mawatha near Narammala Bus Stand and Hospital Mawatha from Peralaswella | Kurunegala | Kuliyapitiya | Thushara roofing (pvt) ltd | 65% | 10696008.28 | 11985499.69 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-05-04 | 2026-08-02