## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/11/25/01/NP/MNR | RR/RDA/11/25/01 | Mahilankulam Pallamadhu road | Mannar | Mannar | George Steuart Engineering (Pvt)Ltd | 50% | 189602588.3 | 274228723.54 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-26 | 2026-05-25
RR/RDA/11/25/02/NP/MNR | RR/RDA/11/25/02 | Piramanayankulam Parappukadanthan road | Mannar | Mannar | George Steuart Engineering (Pvt)Ltd | 55% | 169538631.82 | 244135763.06 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-26 | 2026-05-25
RR/RDA/11/25/03/NP/MNR | RR/RDA/11/25/03 | Kaddadivayal Ramayankulam Naddankandal road | Mannar | Mannar | Nimna Holdings (Pvt) Ltd | 0% | 397160000 | 534364027.24 | Awarded | Tender Above 50Mn
RR/RDA/11/25/04/NP/MNR | RR/RDA/11/25/04 | Tharavankottai to Keeri Main Road | Mannar | Mannar | VN Construction JV | 60% | 146489579.5 | 76333504.2 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-04 | 2026-06-04
RR/RDA/11/25/07/NP/MNR | RR/RDA/11/25/07 | Avithappar Panimayam Internal Road with Culvert - Pesalai | Mannar | Mannar | VN Construction JV | 70% | 0 | 85087335.02 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-04 | 2026-06-04
RR/RDA/11/25/11/NP/MNR | RR/RDA/11/25/11 | Eruvittan - Vellalakaddu Road | Mannar | Mannar | VN Construction JV | 5% | 0 | 57826727.83 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-04 | 2026-06-04
RR/RDA/11/25/05/NP/MNR | RR/RDA/11/25/05 | Konnayan Kudiyiruppu Internal Main Road | Mannar | Mannar | Sun Constructions (Pvt) Ltd. | 5% | 90000000 | 135947165.98 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-08 | 2026-05-09
RR/RDA/11/25/06/NP/MNR | RR/RDA/11/25/06 | Martin Road | Mannar | Mannar | Pastini Construction Material Supply | 60% | 26739158.6 | 41945343.47 | Awarded | Tender Below 50Mn | Yes | Yes | Yes
RR/RDA/11/25/09/NP/MNR | RR/RDA/11/25/09 | Renovation of Mathirikiramam internal Road Naruvilikulam | Mannar | Mannar | Abdul Cader Constructions | 70% | 28422878 | 40820067.58 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-17 | 2026-03-11
RR/RDA/11/25/10/NP/MNR | RR/RDA/11/25/10 | Malikaippiddy 1st 2nd 3rd 4th Road | Mannar | Mannar | Vision Lanka Engineering (Pvt) Ltd | 100% | 22726000 | 30421965.37 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-26
RR/RDA/11/25/13/NP/MNR | RR/RDA/11/25/13 | Variveli Pandaraveli Road | Mannar | Mannar | Sanjeeve Construction Work | 100% | 29619833.65 | 42658765.29 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-01-30
RR/RDA/11/25/14/NP/MNR | RR/RDA/11/25/14 | Pichaivanifa Nedunkulam Scheme Internal Road 2 | Mannar | Mannar | Fahim Builders | 100% | 14944097.22 | 22523861.72 | Awarded | Tender Below 50Mn | Yes | Yes | Yes
RR/RDA/11/25/15/NP/MNR | RR/RDA/11/25/15 | Veppankulam Scheme Internal Road (Mosque) 3 | Mannar | Mannar | Sanjeeve Construction Work | 100% | 17836311.35 | 24802089.31 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-01-23
RR/RDA/11/25/16/NP/MNR | RR/RDA/11/25/16 | P.P.Potkerny Scheme Internal Road 1 | Mannar | Mannar | Abdul Cader Constructions | 70% | 14295963 | 20672459.81 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-02
RR/RDA/11/25/18/NP/MNR | RR/RDA/11/25/18 | Akaththimurippu Internal Road 3 | Mannar | Mannar | Abdul Cader Constructions | 70% | 15815393 | 23278986.71 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-02
RR/RDA/11/25/19/NP/MNR | RR/RDA/11/25/19 | Chilawathurai Maiyavadi Road | Mannar | Mannar | Abdul Cader Constructions | 100% | 22899536 | 34056451.63 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-01
RR/RDA/11/25/20/NP/MNR | RR/RDA/11/25/20 | Kondachchi to Pasithenral Road | Mannar | Mannar | Abdul Cader Constructions | 70% | 18513473 | 28462180.38 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-01
RR/RDA/11/25/22/NP/MNR | RR/RDA/11/25/22 | School back side road | Mannar | Mannar | Sintha Construction (Pvt) Ltd | 30% | 17295437.5 | 24840827.25 | Awarded | Tender Below 50Mn | Yes | Yes | Yes
RR/RDA/11/25/23/NP/MNR | RR/RDA/11/25/23 | Palakaimunai Beach Road | Mannar | Mannar | Sun Constructions (Pvt) Ltd. | 20% | 111500000 | 184321656.31 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01
RR/RDA/11/25/24/NP/MNR | RR/RDA/11/25/24 | Murukan Kovil Main Road | Mannar | Mannar | Abdul Cader Constructions | 100% | 36558775 | 59821861.03 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01
RR/RDA/11/25/12 |  | Renovation of Chemmantheevu 4th Cross Street. | Mannar | Mannar |  | 100% | 25184287.62 | 25184287.62 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21 | 2025-10-31
RR/RDA/11/25/17 |  | Alakkatu Internal Road 5 | Mannar | Mannar |  | 100% | 25141870.23 | 25141870.23 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-14 | 2025-12-13 | 2025-11-04