## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/05/25/09/CP/MTL | RR/RDA/05/25/09 | Ilukkumbura Samurdhi karyalaya asala Patti ela pilama dakwa | Matale | Matale | Pragathi Civil Contractor | 80% | 38748820 | 41365188.3 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-23 | 2026-02-15
RR/RDA/05/25/10/CP/MTL | RR/RDA/05/25/10 | Sonuththa pradana margaye Shailatharamaya idiriye sita 80 yaya dakwa | Matale | Nalanda | NAGMA ENGINEERING (PVT) LTD | 70% | 56167707.75 | 79104652.3 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-24 | 2026-04-27 | 2026-05-31
RR/RDA/05/25/30/CP/MTL | RR/RDA/05/25/30 | Ganadewi pilimaya asala Kulathunga mahathage welanda sala dakwa | Matale | Nalanda | Lahiru Construction & Consultants (PVT) Ltd | 60% | 59540000 | 77270301.29 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-10 | 2026-08-10 | 2026-08-10
RR/RDA/05/25/23 |  | Manchanayake shed eka asala sita sampath waththa haraha Galketiyawa margaya | Matale | Nalanda |  | 60% | 28401905.12 | 28401905.12 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-12-13 | 2026-06-13
RR/RDA/05/25/28 |  | Adawala Udagama Road | Matale | Nalanda |  | 75% | 56161142.68 | 56161142.68 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2025-09-22 | 2026-02-22 | 2026-04-20