## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/25/08/03/SP/MTR | RR/RDA/25/08/03 | Wattakgoda Ayurvedha Rohala Margaya Sanwardanay kirima | Matara | Matara | Visula Construction | 100% | 33591312.7 | 40420715.27 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-01-24
RR/RDA/25/08/08/SP/MTR | RR/RDA/25/08/08 | Asmagoda Galabadahena Margaya Sanwardanaya Palamu Adiyara | Matara | Deniyaya | Induwara Construction | 100% | 11168036 | 14394112.26 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-17 | 2026-01-16 | 2026-02-16
RR/RDA/25/08/10/SP/MTR | RR/RDA/25/08/10 | Arapotha Belideniya Margaya Carpet athura Sanwardanaya Kirima | Matara | Matara | Rathna Construction | 100% | 22859983.85 | 32189689.87 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-23 | 2025-12-23 | 2026-01-08
RR/RDA/25/08/12/SP/MTR | RR/RDA/25/08/12 | Nawalahena Palamu Para Sanwardanaya Kirima (Jagath Mahathage Niwasa asala sita Kuruppu Mahathage Niwasa Dakwa) | Matara | Matara | Rathnayake Construction | 100% | 5399259.8 | 7523859.66 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-17 | 2026-01-16 | 2026-01-22
RR/RDA/08/25/13/SP/MTR | RR/RDA/08/25/13 | Heelakanda Kanishta Vidyalaya asala sita Budu Medura Dakwa margaya Sanwardanaya Kirima | Matara | Matara | Madurapperuma Construction & Supply | 100% | 8331854.95 | 12476822.24 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-06 | 2026-01-05 | 2026-01-17
RR/RDA/08/25/14/SP/MTR | RR/RDA/08/25/14 | Kanaththewatta kade asala sita Mulana Ela Margaya Dakwa Sanwardanaya Kirima (Pethibemi Sahithawa) | Matara | Matara | Madurapperuma Construction & Supply | 100% | 12885039.94 | 18602255.2 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-06 | 2026-01-05 | 2026-02-11
RR/RDA/08/25/15/SP/MTR | RR/RDA/08/25/15 | Pasal Mawathe Weerathunga Petti Bokkuwa Asala Sita Iriyagaha Mulana Bokkuwa Dakwa Pethi Bemi yoda Sanwardanaya Kirima | Matara | Matara | Madurapperuma Construction & Supply | 100% | 20214236.58 | 32183364.43 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-06 | 2026-01-05 | 2025-02-06
RR/RDA/08/25/16/SP/MTR | RR/RDA/08/25/16 | Walgama Saddathissa Mawathe Primesity Niwasa Sankeernaye Prawesha Margaya Kapat yoda Sanwardanaya kirima | Matara | Matara | Jagath construction | 100% | 7623062.15 | 13010600.06 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-24 | 2026-01-23 | 2025-01-07
RR/RDA/08/25/18/SP/MTR | RR/RDA/08/25/18 | Dekatukella Margaya Pethibemma sahithawa Sanwardanaya kirima | Matara | Matara | Dashodhaya (Pvt)Ltd | 0% | 4080866.9 | 6117703.11 | Awarded | Tender Below 50Mn |  |  |  | 2025-10-09 | 2026-01-08 | 2025-12-16
RR/RDA/08/25/19/SP/MTR | RR/RDA/08/25/19 | Sahakara wathu Adikari nila niwasa asala sita koppara weediya pittaniya dakwa margaya Sanwardanaya kirima | Matara | Deniyaya | Gamage Builders | 100% | 10371473.2 | 14049577.09 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-06 | 2026-01-05 | 2025-12-16
RR/RDA/08/25/20/SP/MTR | RR/RDA/08/25/20 | Naymbala kendawala haraha wellethota margaye wedugoda sthanaye pethi bemma sahithawa Sanwardanaya kirima | Matara | Matara | Rathnayake Construction | 100% | 3502675 | 4877230.33 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-15 | 2026-01-14 | 2025-12-12
| RR/RDA/08/25/26 | Development of the road by laying Asphalt starting from near Saddhatissa Junior College on the Panattiyana-Weligama road up to Barawadeniya Junction | Matara |  | GEL Construction | 0% | 135290000 | 159903564.25 | Awarded | Tender Above 50Mn
| RR/RDA/08/25/27 | Development of the Pathegama Temple Road (Massalatiya Road) by carpeting | Matara |  | GEL Construction | 0% | 81100000 | 86763583.11 | Awarded | Tender Above 50Mn
RR/RDA/25/08/07 |  | Ovitigamuwa Alahenpita margaya Sanwardanaya Kirima (RDA yatathe Idikirima Arambha kara atharamaga nawatha etha) | Matara | Matara |  | 100% | 29034089.99 | 29034089.99 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-22
RR/RDA/25/08/01 |  | Kajjuhena Margaya Sanwardanaya Kirima (Kajjuhena Handiya Sita Alikavila Budu Madura Dakwa ) I adiyara | Matara | Deniyaya |  | 100% | 78061393.44 | 78061393.44 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-10-15 | 2026-01-31
RR/RDA/25/08/06 |  | Samarasinghe Mawathw Ithiri Kotasa Sanwardanaya Kirima | Matara | Matara |  | 100% | 17005961.71 | 16851257.35 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-10-30 | 2025-11-15
RR/RDA/25/08/11 |  | Thambagala Margaya Sanwardanaya Kirima (Highway pitawime sthanayen arambha vi Pradeepa Mahathmiyage Niwasa dakwa Kotasa) | Matara | Matara |  | 100% | 9396645.17 | 9425286.29 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-09-15
RR/RDA/08/25/23 |  | Epitakaduwa Krishantha Senarath Yapa Road (Eptakaduwa Budu medura to Mr. LG Jagath Yapa home) | Matara | Matara |  | 100% | 7231417.22 | 7231417.22 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 | 2025-11-16 | 2025-10-31
RR/RDA/08/25/22 |  | Kirinda Roundabout Road with drainages | Matara | Matara |  | 100% | 23083588.28 | 23083588.28 | Awarded | DL Stage 04 | Yes | Yes | Yes |  |  | 2026-02-28
RR/RDA/08/25/02 |  | Andaledduwa Road | Matara | Matara |  | 100% | 24533049.28 | 24533049.28 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 |  | 2026-02-28