## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
| RR/RDA/23/25/44 | Kiriibban wewa Ayurweda road | Monaragala | Monaragala | U P Ranugge Construction (Pvt) Ltd | 100% | 34095028 | 53343034.36 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-12
RR/RDA/23/25/01 |  | Puwakgoda Uramada Margaya K.M.Thilak Bandara Mahathage niwasa idiripita sita ema Margayema R.M.Punchi Nona Mahathmiyage Niwasa Dakwa Margaya | Monaragala | Bibile |  | 100% | 64599474.91 | 64599474.91 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-15
RR/RDA/23/25/04 |  | Walawegaga Asala (Nildiya Mankada) Sita Udawalawa Bant eka Dakwa | Monaragala | Monaragala |  | 100% | 74104374.63 | 74104374.63 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-15 | 2025-10-31
RR/RDA/23/25/03 |  | Liyangolla Lolla Margaya | Monaragala | Bibile |  | 100% | 38879897 | 38879897 | Awarded | DL Stage 02 | Yes | Yes | Yes |  | 2025-10-30 | 2025-11-30
RR/RDA/23/25/02 |  | Uduwara wewa Handiya sita Athula Margaya | Monaragala | Bibile |  | 100% | 34079767.34 | 34079767.34 | Awarded | DL Stage 02 | Yes | Yes | Yes |  | 2025-10-30 | 2025-11-30