## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/13/25/01/NP/MUL | RR/RDA/13/25/01 | Akkaraiveli Paraiyanaru ( Vilaththiyad) Road Package 1 | Mullaitivu | Mullaitivu | Sun Constructions (Pvt) Ltd. | 0% | 145000000 | 188808095.02 | Awarded | Tender Above 50Mn |  |  |  | 2025-12-02 | 2026-03-02
RR/RDA/13/25/03/NP/MUL | RR/RDA/13/25/03 | Navatkadu Road | Mullaitivu | Mullaitivu | TMC Constructions | 60% | 50363687 | 77969519 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-01 | 2026-06-06
RR/RDA/13/25/06/NP/MUL | RR/RDA/13/25/06 | Pandaravanniyan Silaiyadi Road | Mullaitivu | Mullaitivu | Sun Constructions (Pvt) Ltd. | 40% | 83700000 | 113438730.78 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-26 | 2026-03-26
RR/RDA/13/25/07/NP/MUL | RR/RDA/13/25/07 | Kanagarayankulam District Boundary Road (Old Kandy road) | Mullaitivu | Mullaitivu | Sun Constructions (Pvt) Ltd. | 60% | 159972500 | 220671169.9 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-26 | 2026-03-26 | 2026-06-12
RR/RDA/13/25/08/NP/MUL | RR/RDA/13/25/08 | Kumulamunai Akkarayan road | Mullaitivu | Mullaitivu | Nimna Holdings (Pvt) Ltd | 70% | 148861042 | 198505802.7 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-01 | 2026-06-20
RR/RDA/13/25/10/NP/MUL | RR/RDA/13/25/10 | Pandiyankulam Neddankandal Road | Mullaitivu | Mullaitivu | Nimna Holdings (Pvt) Ltd | 70% | 144696282.5 | 191627958.51 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-01 | 2026-06-10
RR/RDA/13/25/11/NP/MUL | RR/RDA/13/25/11 | Ethawetuvuwewa to Sampathnuwara | Mullaitivu | Mullaitivu | Nimna Holdings (Pvt) Ltd | 30% | 110422944.5 | 141810206.62 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-22 | 2026-06-22
RDA/GOSL/NP/RR/LCB/PACKAGE 2(MU) | NMU039 | Thapaalaga veethi Section I &II, 2nd Cross Road, Kallappadu kadtkarai Main Road, Koolamurippu kerudamadu enaippu veethi and Olumadu Pullmachchinathikulam Ampakamam Road | Mullaitivu |  | RR Construction (Pvt) Ltd. | 0% | 659118972.33 | 586656287.93 | Awarded | PIU
RR/RDA/13/25/09 |  | Aninchiyankulam 2nd Lane MUTE095 | Mullaitivu | Mullaitivu |  | 100% | 46445947.77 | 46445947.77 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-11-21 | 2025-09-21
RR/RDA/13/25/04 |  | Suthanthirapuram Main Road Package 1 | Mullaitivu | Mullaitivu |  | 100% | 110821121.4 | 110821121.4 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-13 | 2025-11-12 | 2025-11-30
RR/RDA/13/25/05 |  | Suthanthirapuram Main Road Package 2 | Mullaitivu | Mullaitivu |  | 100% | 63852534.37 | 63852534.37 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 | 2025-11-30 | 2026-02-06
RR/RDA/13/25/02 |  | Kokkilai Estuary fishing village Road | Mullaitivu | Mullaitivu |  | 100% | 26445698.08 | 26445698.08 | Awarded | DL Stage 04 | Yes | Yes | Yes |  |  | 2026-03-31