## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/13/25/01/NP/MUL | RR/RDA/13/25/01 | Akkaraiveli Paraiyanaru ( Vilaththiyad) Road Package 1 | Mullaitivu | Mullaitivu | Sun Constructions (Pvt) Ltd. | 0% | 145000000 | 188808095.02 | Awarded | Tender Above 50Mn |  |  |  | 2025-12-02 | 2026-03-02
RR/RDA/13/25/03/NP/MUL | RR/RDA/13/25/03 | Navatkadu Road | Mullaitivu | Mullaitivu | TMC Constructions | 60% | 50363687 | 77969519 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-01 | 2026-06-06
RR/RDA/13/25/06/NP/MUL | RR/RDA/13/25/06 | Pandaravanniyan Silaiyadi Road | Mullaitivu | Mullaitivu | Sun Constructions (Pvt) Ltd. | 40% | 83700000 | 113438730.78 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-26 | 2026-03-26
RR/RDA/13/25/07/NP/MUL | RR/RDA/13/25/07 | Kanagarayankulam District Boundary Road (Old Kandy road) | Mullaitivu | Mullaitivu | Sun Constructions (Pvt) Ltd. | 60% | 159972500 | 220671169.9 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-26 | 2026-03-26 | 2026-06-12
RR/RDA/13/25/08/NP/MUL | RR/RDA/13/25/08 | Kumulamunai Akkarayan road | Mullaitivu | Mullaitivu | Nimna Holdings (Pvt) Ltd | 70% | 148861042 | 198505802.7 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-01 | 2026-06-20
RR/RDA/13/25/10/NP/MUL | RR/RDA/13/25/10 | Pandiyankulam Neddankandal Road | Mullaitivu | Mullaitivu | Nimna Holdings (Pvt) Ltd | 70% | 144696282.5 | 191627958.51 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-01 | 2026-06-10