## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/19/25/04/NWP/PUT | RR/RDA/19/25/04 | Carpeting of green light carpeted road from Bogus Junction (80 acres). | Puttalam | Chilaw | Sri Ram Constructions | 65% | 34055720.05 | 59154724.51 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-09 | 2026-03-09 | 2026-06-09
RR/RDA/19/25/27/NWP/PUT | RR/RDA/19/25/27 | The entrance to the Medical Officer's Office in the Galahitiyawa Grama Niladhari Division | Puttalam | Chilaw | Omega Construction (Pvt) Ltd | 60% | 38495776 | 49714778.94 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-05 | 2026-02-03 | 2026-06-03
RR/RDA/19/25/37/NWP/PUT | RR/RDA/19/25/37 | Lawyer Wijayananda's House Road | Puttalam | Chilaw | Ponnamperuma Suppliers | 70% | 7763919.68 | 9913614.44 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-13 | 2026-04-14 | 2026-06-13
RR/RDA/19/25/38/NWP/PUT | RR/RDA/19/25/38 | North Dummaladeniya Cross Road | Puttalam | Chilaw | Ponnamperuma Suppliers | 90% | 10005001.78 | 11621041.2 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-14 | 2026-04-14 | 2026-04-14
| RR/RDA/19/25/91 | Development of Fenando Road - Picchawala Road | Puttalam | Chilaw | Dilini Builders (PVT) LTD | 0% | 26046308.34 | 27030199.65 | Awarded | Tender Below 50Mn |  |  |  | 2026-05-20 | 2026-08-17
RR/RDA/19/25/09 |  | Water front Mawatha (wennappuwa) | Puttalam | Chilaw |  | 100% | 12072583.1 | 12072583.1 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/19/25/07 |  | Development of the road from near Kalegama School to Erungwila. | Puttalam | Chilaw |  | 100% | 55009126.14 | 55009126.14 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 |  | 2025-10-31
RR/RDA/19/25/25 |  | Development of Mada Koswadiya Bogaha Road | Puttalam | Chilaw |  | 100% | 25235881.81 | 25235881.81 | Awarded | DL Stage 03 | Yes | Yes | Yes |  |  | 2025-11-05
RR/RDA/19/25/36 |  | Renovation of Warusavithana Laboratory Road | Puttalam | Chilaw |  | 65% | 19592732.06 | 19592732.06 | Awarded | DL Stage 04 | Yes | Yes | Yes |  |  | 2026-03-31