## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/19/25/38/NWP/PUT | RR/RDA/19/25/38 | North Dummaladeniya Cross Road | Puttalam | Chilaw | Ponnamperuma Suppliers | 90% | 10005001.78 | 11621041.2 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-14 | 2026-04-14 | 2026-04-14
RR/RDA/19/25/39/NWP/PUT | RR/RDA/19/25/39 | Renovation of Khemananda Road | Puttalam |  | SriLak Import and Export Company | 95% | 19114271.45 | 22000226.26 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-19 | 2026-04-19 | 2026-04-19