## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/19/25/26/NWP/PUT | RR/RDA/19/25/26 | Abayarama Mawatha Bomimakka Kovil Road to Sembandaluwa Temple Road | Puttalam | Puttalam | Sampath Construction | 100% | 26275458.07 | 42010632 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-05 | 2026-02-05 | 2026-02-03
RR/RDA/19/25/28/NWP/PUT | RR/RDA/19/25/28 | Samagi Mawatha | Puttalam | Puttalam | Ranuja Construction | 100% | 25908850 | 36001594.79 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-15 | 2026-04-15 | 2026-06-15
RR/RDA/19/25/29/NWP/PUT | RR/RDA/19/25/29 | Development of the road from Galkuliya Welameda to Mrs. Deepani's house | Puttalam | Puttalam | Sampath Construction | 100% | 8675871.6 | 13481102.43 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-15 | 2026-04-15 | 2026-06-15
| RR/RDA/19/25/40 | Development of the road from Madurankuliya to Velasiya College | Puttalam | Puttalam | Sampath Construction | 30% | 55254878 | 90437412.35 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-20 | 2026-05-21
RR/RDA/19/25/09 |  | Water front Mawatha (wennappuwa) | Puttalam | Chilaw |  | 100% | 12072583.1 | 12072583.1 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/19/25/03 |  | Nawagattegama Rohala Pare sita Thapal Karyalaya Dakwa margaya (Nawagattegama) | Puttalam | Puttalam |  | 100% | 23512239.79 | 23512239.79 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/19/25/02 |  | Concrete development of the road from Hopper Kada junction to Elu Farm. | Puttalam | Puttalam |  | 100% | 33229489.54 | 33229489.54 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 |  | 2026-01-31
RR/RDA/19/25/07 |  | Development of the road from near Kalegama School to Erungwila. | Puttalam | Chilaw |  | 100% | 55009126.14 | 55009126.14 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 |  | 2025-10-31
RR/RDA/19/25/25 |  | Development of Mada Koswadiya Bogaha Road | Puttalam | Chilaw |  | 100% | 25235881.81 | 25235881.81 | Awarded | DL Stage 03 | Yes | Yes | Yes |  |  | 2025-11-05
RR/RDA/19/25/36 |  | Renovation of Warusavithana Laboratory Road | Puttalam | Chilaw |  | 65% | 19592732.06 | 19592732.06 | Awarded | DL Stage 04 | Yes | Yes | Yes |  |  | 2026-03-31
RR/RDA/19/25/35 |  | Carpeting & Development of Kolithatissa Mawatha | Puttalam | Puttalam |  | 100% | 10359335.01 | 10359335.01 | Awarded | DL Stage 04 | Yes | Yes | Yes |  |  | 2026-03-31