## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/25/24/02/SBP/RTP | RR/RDA/25/24/02 | Thundola Varathenna Road | Ratnapura | Embilipitiya | Siri Construction | 35% | 123540895.5 | 122516687.81 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-05-02 | 2026-04-27
RR/RDA/25/24/08 |  | From Mr.Ranjth's House to Mr.Premasiri's House in Maduwanwela Janapadaya 2nd Lane Road | Ratnapura | Embilipitiya |  | 100% | 39030233.29 | 39030233.29 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/25/24/35 |  | Ilumba Kanda Road from Milinduthalawa Temple | Ratnapura | Embilipitiya |  | 30% | 24709638.71 | 24709638.71 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 | 2026-03-31 | 2026-04-10
RR/RDA/25/24/17 |  | Pahalawaththa to Batahenkanda Road | Ratnapura | Embilipitiya |  | 10% | 112040241.38 | 112040241.38 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 | 2026-03-31 | 2026-04-10
RR/RDA/25/24/19 |  | Wijeriya Iththekanda Margaya Sanwardanaya Kirima | Ratnapura | Embilipitiya |  | 35% | 72158727.69 | 72158727.69 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 | 2026-03-31 | 2026-04-10
RR/RDA/25/24/20 |  | Godawela Walakada margaya Sanwardanaya Kirima (Walakada Junction to Godawela Junction) | Ratnapura | Embilipitiya |  | 15% | 126132479.8 | 126132479.8 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 | 2026-03-31 | 2026-04-10