## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/25/24/01/SBP/RTP | RR/RDA/25/24/01 | From Delgas Junction To Vilehena Road | Ratnapura | Ratnapura | Siri Construction | 90% | 30346327.41 | 43303726.54 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-15
RR/RDA/25/24/03/SBP/RTP | RR/RDA/25/24/03 | From Thunaghahena To Temple Road | Ratnapura | Ratnapura | Siri Construction | 95% | 20065425.82 | 27753891.86 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-15
RR/RDA/25/24/10/SBP/RTP | RR/RDA/25/24/10 | From Deniya kade Market to Henyaya Road Via Keenagahaella Road | Ratnapura | Pelmadulla | Sam Dam | 95% | 31673916.45 | 50516461.34 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-27