## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/17/25/05/EP/TRN | RR/RDA/17/25/05 | Improvement to Jeyanthiwewa to Track 12 Main Road | Trincomalee | Trincomalee | Nirupama Construction | 65% | 103260000 | 160000893.78 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-12 | 2027-03-11 | 2026-09-15
RR/RDA/17/25/06/EP/TRN | RR/RDA/17/25/06 | Malporuwa to Thalgaswewa | Trincomalee | Trincomalee | Jeezan Trading and Transport | 7% | 109630000 | 163676063.08 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-12 | 2027-03-11 | 2026-10-15
RR/RDA/17/25/09/EP/TRN | RR/RDA/17/25/09 | School-Galmetiyawa Main Internal Road | Trincomalee | Trincomalee | Zaka Engineering Consultancy | 50% | 53122107.5 | 77200000 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-05-22 | 2026-08-21 | 2026-07-31
RR/RDA/SP/17/25/03/EP/TRN | RR/RDA/SP/17/25/03 | Hajra Road (Alhira Jalaira Road) | Trincomalee | Trincomalee | STAAR Construction | 40% | 38692742 | 51948669.36 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-05-22 | 2026-08-21