## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/17/25/01/EP/TRN | RR/RDA/17/25/01 | Pillayar Road Renovation | Trincomalee | Trincomalee | Rina Construction | 100% | 23425921.56 | 30058596.03 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-05 | 2026-02-04 | 2025-12-15
RR/RDA/17/25/02/EP/TRN | RR/RDA/17/25/02 | Kathirkamathambi Road | Trincomalee | Trincomalee | Fareed | 100% | 28809738 | 38871590.79 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-05 | 2026-02-04 | 2025-12-15
RR/RDA/17/25/03/EP/TRN | RR/RDA/17/25/03 | Hospital Road | Trincomalee | Trincomalee | Pragash Construction | 100% | 18557253.77 | 23553502.5 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-05 | 2026-02-04 | 2025-12-15
RR/RDA/17/25/07/EP/TRN | RR/RDA/17/25/07 | Kanthamalawa Main Road | Trincomalee | Trincomalee | SSK Construction | 100% | 9161570 | 17579515.67 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-04-23 | 2026-07-23
RR/RDA/17/25/10/EP/TRN | RR/RDA/17/25/10 | From Medagama temple to Peramaduwa | Trincomalee | Trincomalee | Soyuru Sampath Construction & Suppliers | 100% | 24197635 | 31162876.79 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-21 | 2026-02-20 | 2026-01-30
RR/RDA/17/25/11/EP/TRN | RR/RDA/17/25/11 | Development of Road from near the Fair | Trincomalee | Trincomalee | MS Construction | 15% | 25280343.6 | 37892493.36 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-06-04 | 2026-09-03
RR/RDA/17/25/12/EP/TRN | RR/RDA/17/25/12 | Improvement of RDS Road | Trincomalee | Trincomalee | MTA Construction | 100% | 30166053 | 38673984.79 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-04 | 2026-02-03 | 2025-12-15
RR/RDA/17/25/13/EP/TRN | RR/RDA/17/25/13 | Concreting from School junction to Boovidya Office | Trincomalee | Trincomalee | Hana Construction (Pvt) Ltd. | 100% | 38264100 | 49104899.44 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-21 | 2026-02-19 | 2026-07-31
RR/RDA/17/25/14/EP/TRN | RR/RDA/17/25/14 | Amaithusha Road (School road to Vaithiyar road) | Trincomalee | Trincomalee | Shaniff Construction | 100% | 5006100 | 6650570.02 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-21 | 2026-02-19 | 2026-05-30
RR/RDA/17/25/15/EP/TRN | RR/RDA/17/25/15 | Cemetery Road (Sajahan Mowlavi's house to Thajudeen shop) | Trincomalee | Trincomalee | Soyuru Sampath Construction & Suppliers | 100% | 21774456 | 27637562.79 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-05 | 2026-02-04 | 2026-02-04
RR/RDA/17/25/16/EP/TRN | RR/RDA/17/25/16 | Valuvar Road (Main road to Kovil road) | Trincomalee | Trincomalee | Shaniff Construction | 100% | 10783850 | 13997601.51 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-02 | 2026-03-02 | 2026-01-30
RR/RDA/17/25/18/EP/TRN | RR/RDA/17/25/18 | Sooranagar Main Road (Muththuchenai Junction to Thuvaraka Vithiyalayam)-Concrete | Trincomalee | Trincomalee | SSK Construction | 100% | 25155240 | 38483392.5 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-06-02 | 2026-09-01
RR/RDA/17/25/19/EP/TRN | RR/RDA/17/25/19 | Periya Suwami Kovil Road-Concrete | Trincomalee | Trincomalee | Motec Engineering & Construction | 20% | 25774146 | 39914113.43 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-06-04 | 2026-09-03
RR/RDA/SP/17/25/01/EP/TRN | RR/RDA/SP/17/25/01 | Alankerny faisal Main Road (Koof Nagar) | Trincomalee | Trincomalee | NAS Construction | 100% | 26879843.97 | 35125795.85 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-02 | 2026-03-02 | 2026-01-30
RR/RDA/STAII/17/25/03/EP/TRN | RR/RDA/STA II/17/25/03 | From No.908 house to No.904 house road | Trincomalee | Trincomalee | Soyuru Sampath Construction & Suppliers | 15% | 10476638.8 | 14487311.88 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-07 | 2026-11-05
RR/RDA/STAII/17/25/04/EP/TRN | RR/RDA/STA II/17/25/04 | From No.851 house to Rajaela road | Trincomalee | Trincomalee | ARN Engineering & Construction | 15% | 10452104.5 | 13792738.83 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-07 | 2026-11-05
RR/RDA/17/25/10KM/01/EP/TRN | RR/RDA/17/25/10KM/01 | Road behind th hospital up to the morgue junction | Trincomalee | Trincomalee | Soyuru Sampath Construction & Suppliers | 10% | 13214817 | 15950150.82 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-10 | 2026-11-08
RR/RDA/17/25/10KM/02/EP/TRN | RR/RDA/17/25/10KM/02 | LB cannel bridge to pachchimarama temple | Trincomalee | Trincomalee | Rina Construction | 5% | 16850648.32 | 19678704.72 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-10 | 2026-11-08
RR/RDA/17/25/10KM/03/EP/TRN | RR/RDA/17/25/10KM/03 | Ethabendiwewa Second Lane | Trincomalee | Trincomalee | Nathan's Construction | 90% | 38931574 | 46705794.64 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-07 | 2026-11-05
RR/RDA/17/25/10KM/04/EP/TRN | RR/RDA/17/25/10KM/04 | Kajuwaththa gama meda road | Trincomalee | Trincomalee | NMST Construction | 5% | 22770000 | 29466015.3 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-07-31 | 2026-10-29
RR/RDA/17/25/10KM/06/EP/TRN | RR/RDA/17/25/10KM/06 | Budu pilima and 4th lane road | Trincomalee | Trincomalee | RS Construction | 15% | 17520285.64 | 28351870.49 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-07-31 | 2026-10-29
RR/RDA/17/25/10KM/07/EP/TRN | RR/RDA/17/25/10KM/07 | Kawanthissa mawatha and in front of the cementerv road | Trincomalee | Trincomalee | Rina Construction | 20% | 15075988.4 | 20683158.47 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-10 | 2026-11-08
RR/RDA/17/25/10KM/08/EP/TRN | RR/RDA/17/25/10KM/08 | Paththini Amman Kevil road | Trincomalee | Trincomalee | Alpha Engineering Services & Suppliers | 25% | 30365709 | 46089014.73 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-04 | 2026-11-03
RR/RDA/17/25/10KM/09/EP/TRN | RR/RDA/17/25/10KM/09 | Bazar mosque road | Trincomalee | Trincomalee | MTA Construction | 40% | 32616074.7 | 44293054.87 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-04 | 2026-11-03
RR/RDA/17/25/04 |  | Cemetry Road (Poompuhr) | Trincomalee | Trincomalee |  | 100% | 32194573.49 | 32194573.49 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-22
RR/RDA/17/25/17 |  | Furkaniya Marcus connection road (S.M.Unithu house to Market main road) | Trincomalee | Trincomalee |  | 100% | 15444993.23 | 15444993.23 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-09-30