## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/12/25/02/NP/VVN | RR/RDA/12/25/02 | Eswarypuram housing scheme internal road (NVSTE178) | Vavuniya | Vavuniya | Sintha Construction (Pvt) Ltd | 100% | 28833609.2 | 40810577.98 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/05/NP/VVN | RR/RDA/12/25/05 | Sinnakulam road – laxapana road | Vavuniya | Vavuniya | Arul Selvi Construction and Hardware | 100% | 16411999.99 | 21459717.36 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-13 | 2026-02-13
RR/RDA/12/25/08/NP/VVN | RR/RDA/12/25/08 | Katkulam road | Vavuniya | Vavuniya | Yansika Success Group (Pvt) Ltd | 100% | 18055415.95 | 22884956.34 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-03 | 2026-03-04
RR/RDA/12/25/26/NP/VVN | RR/RDA/12/25/26 | Cemetery Road | Vavuniya | Vavuniya | Ranasinghe Construction | 100% | 17011533 | 23875168.24 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06
RR/RDA/12/25/30/NP/VVN | RR/RDA/12/25/30 | Maradammaduwa Rural Road | Vavuniya | Vavuniya | Sevvel Construction & Suppliers | 100% | 25533435.95 | 33292513.97 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-17 | 2026-03-18
RR/RDA/12/25/32/NP/VVN | RR/RDA/12/25/32 | Kalukummankaduwa to Alagalla Rural Road | Vavuniya | Vavuniya | Yansika Construction | 100% | 36671440.85 | 61020259.1 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-02 | 2026-03-04
RR/RDA/12/25/33/NP/VVN | RR/RDA/12/25/33 | Mamaduwa Thiyawaragama Road | Vavuniya | Vavuniya | 5N Group Construction | 100% | 20811747 | 26687363.08 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-17 | 2026-02-21
RR/RDA/12/25/36/NP/VVN | RR/RDA/12/25/36 | Mamaduwa to Dikwewa | Vavuniya | Vavuniya | Sintha Construction (Pvt) Ltd | 100% | 18006430.2 | 25629657.32 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/37/NP/VVN | RR/RDA/12/25/37 | Parakumawatha | Vavuniya | Vavuniya | Ranasinghe Construction | 100% | 26672047.6 | 34830175.61 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-24 | 2026-01-23
RR/RDA/12/25/39/NP/VVN | RR/RDA/12/25/39 | Madukanda lake side road | Vavuniya | Vavuniya | Sintha Construction (Pvt) Ltd | 100% | 22687590.2 | 31883174.61 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/42/NP/VVN | RR/RDA/12/25/42 | Veerapuram main road (veerapuram 2nd 3rd lane) | Vavuniya | Vavuniya | Yaso Engineering | 100% | 19745000 | 25380543.51 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06
RR/RDA/12/25/46/NP/VVN | RR/RDA/12/25/46 | Sinnasippikulam to neriyakulam road | Vavuniya | Vavuniya | North Construction (Pvt) Ltd | 100% | 14561522.25 | 21276360.97 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/53/NP/VVN | RR/RDA/12/25/53 | Ethawetunuwewa Temple Road | Vavuniya | Vavuniya | Shiyamala Construction | 100% | 9515000 | 12174775.32 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-05
RR/RDA/12/25/55/NP/VVN | RR/RDA/12/25/55 | Mayawewa to Namalpura Road | Vavuniya | Vavuniya | Yansika Construction | 100% | 17639615.95 | 22825561.83 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-05
RR/RDA/12/25/56/NP/VVN | RR/RDA/12/25/56 | From Nikawewa Post Office to Nikawewa Right Village | Vavuniya | Vavuniya | Yansika Construction | 100% | 17924713.95 | 23412051.37 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-05
RR/RDA/12/25/57/NP/VVN | RR/RDA/12/25/57 | Nikawewa Right to Sapumalthanna | Vavuniya | Vavuniya | Yansika Construction | 100% | 11848115.95 | 15184106.87 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-05
RR/RDA/12/25/58/NP/VVN | RR/RDA/12/25/58 | Preschool Road | Vavuniya | Vavuniya | 5N Group Construction | 100% | 21518222 | 28313232.5 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-10 | 2026-02-08
RR/RDA/12/25/59/NP/VVN | RR/RDA/12/25/59 | Kalyanipura 2nd lane | Vavuniya | Vavuniya | 5N Group Construction | 100% | 28184992 | 37048858.38 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-12
RR/RDA/12/25/44 |  | Menicfarm school road (0.5km) (NVVPE97) | Vavuniya | Vavuniya |  | 100% | 11100861.98 | 11100861.98 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/12/25/06 |  | Paalavinayagar road | Vavuniya | Vavuniya |  | 100% | 17373382.99 | 18688450.91 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-14 | 2025-11-13 | 2026-02-28
RR/RDA/12/25/11 |  | Madeenanagar road | Vavuniya | Vavuniya |  | 100% | 21394474.49 | 21394474.49 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-10-16 | 2025-11-01 | 2025-11-01