## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/12/25/02/NP/VVN | RR/RDA/12/25/02 | Eswarypuram housing scheme internal road (NVSTE178) | Vavuniya | Vavuniya | Sintha Construction (Pvt) Ltd | 100% | 28833609.2 | 40810577.98 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/17/NP/VVN | RR/RDA/12/25/17 | Lyca village enterance Road | Vavuniya | Vavuniya | Sun Constructions (Pvt) Ltd. | 35% | 0 | 54064384.24 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-05 | 2026-06-03
RR/RDA/12/25/22/NP/VVN | RR/RDA/12/25/22 | Mannankerny road | Vavuniya | Vavuniya | Sun Constructions (Pvt) Ltd. | 50% | 0 | 51515196.2 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-05 | 2026-06-03
RR/RDA/12/25/52/NP/VVN | RR/RDA/12/25/52 | Menanager Malakattu Kalkuwari Road | Vavuniya | Vavuniya | Sun Constructions (Pvt) Ltd. | 65% | 0 | 54861523.89 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-05 | 2026-06-03
RR/RDA/12/25/05/NP/VVN | RR/RDA/12/25/05 | Sinnakulam road – laxapana road | Vavuniya | Vavuniya | Arul Selvi Construction and Hardware | 100% | 16411999.99 | 21459717.36 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-13 | 2026-02-13
RR/RDA/12/25/08/NP/VVN | RR/RDA/12/25/08 | Katkulam road | Vavuniya | Vavuniya | Yansika Success Group (Pvt) Ltd | 100% | 18055415.95 | 22884956.34 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-03 | 2026-03-04
RR/RDA/12/25/18/NP/VVN | RR/RDA/12/25/18 | Nedunkerny North sandankulam Road | Vavuniya | Vavuniya | Yaso Engineering | 35% | 32829160.1 | 46839314.91 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-12
RR/RDA/12/25/19/NP/VVN | RR/RDA/12/25/19 | Senaipilavu Road | Vavuniya | Vavuniya | Yaso Engineering | 70% | 32576225 | 43285227.82 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-12
RR/RDA/12/25/20/NP/VVN | RR/RDA/12/25/20 | Puthiyakudiyiruppu parasankulam road | Vavuniya | Vavuniya | Bapithan Construction | 70% | 23259239.3 | 34966229.53 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06
RR/RDA/12/25/21/NP/VVN | RR/RDA/12/25/21 | Bagaswewa 01st 22nd lane | Vavuniya | Vavuniya | Bapithan Construction | 35% | 22749983.3 | 33747516.65 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06
RR/RDA/12/25/24/NP/VVN | RR/RDA/12/25/24 | Kanagarayankulam puthuvilankulam road (NVVNE073) | Vavuniya | Vavuniya | Bapithan Construction | 70% | 31165786.3 | 46468981.72 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-13
RR/RDA/12/25/25/NP/VVN | RR/RDA/12/25/25 | 2nd cross Lane Ginigathhena | Vavuniya | Vavuniya | Nimna Holdings (Pvt) Ltd | 70% | 27770291 | 40686140.26 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-17 | 2026-02-21
RR/RDA/12/25/26/NP/VVN | RR/RDA/12/25/26 | Cemetery Road | Vavuniya | Vavuniya | Ranasinghe Construction | 100% | 17011533 | 23875168.24 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06
RR/RDA/12/25/27/NP/VVN | RR/RDA/12/25/27 | From Acre 400 7th Lane to cross end of the 2nd internal road close to Andarawewa | Vavuniya | Vavuniya | Ranasinghe Construction | 30% | 46360659.24 | 57948785.02 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-02 | 2026-03-03
RR/RDA/12/25/28/NP/VVN | RR/RDA/12/25/28 | From Janaudanagama 2nd internal road to end of the free school | Vavuniya | Vavuniya | North Construction (Pvt) Ltd | 35% | 26569012.25 | 37396800.47 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06
RR/RDA/12/25/29/NP/VVN | RR/RDA/12/25/29 | Kalasiyambalawa Road | Vavuniya | Vavuniya | North Construction (Pvt) Ltd | 50% | 13504281.45 | 19583811.27 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-13
RR/RDA/12/25/30/NP/VVN | RR/RDA/12/25/30 | Maradammaduwa Rural Road | Vavuniya | Vavuniya | Sevvel Construction & Suppliers | 100% | 25533435.95 | 33292513.97 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-17 | 2026-03-18
RR/RDA/12/25/31/NP/VVN | RR/RDA/12/25/31 | Mahakachchakodiya to Ettambagaskada | Vavuniya | Vavuniya | Yansika Construction | 30% | 45254190.85 | 59974624.42 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-02 | 2026-01-20
RR/RDA/12/25/32/NP/VVN | RR/RDA/12/25/32 | Kalukummankaduwa to Alagalla Rural Road | Vavuniya | Vavuniya | Yansika Construction | 100% | 36671440.85 | 61020259.1 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-02 | 2026-03-04
RR/RDA/12/25/33/NP/VVN | RR/RDA/12/25/33 | Mamaduwa Thiyawaragama Road | Vavuniya | Vavuniya | 5N Group Construction | 100% | 20811747 | 26687363.08 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-17 | 2026-02-21
RR/RDA/12/25/35/NP/VVN | RR/RDA/12/25/35 | Awusadapitiya Pubudugama Road | Vavuniya | Vavuniya | Nimna Holdings (Pvt) Ltd | 70% | 32504637.43 | 46347432.25 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-02 | 2026-02-21
RR/RDA/12/25/36/NP/VVN | RR/RDA/12/25/36 | Mamaduwa to Dikwewa | Vavuniya | Vavuniya | Sintha Construction (Pvt) Ltd | 100% | 18006430.2 | 25629657.32 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/37/NP/VVN | RR/RDA/12/25/37 | Parakumawatha | Vavuniya | Vavuniya | Ranasinghe Construction | 100% | 26672047.6 | 34830175.61 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-24 | 2026-01-23
RR/RDA/12/25/38/NP/VVN | RR/RDA/12/25/38 | Salalinigama 11 lane | Vavuniya | Vavuniya | Sintha Construction (Pvt) Ltd | 50% | 30830906.7 | 40853027.3 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/39/NP/VVN | RR/RDA/12/25/39 | Madukanda lake side road | Vavuniya | Vavuniya | Sintha Construction (Pvt) Ltd | 100% | 22687590.2 | 31883174.61 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/40/NP/VVN | RR/RDA/12/25/40 | Halabagaswewa | Vavuniya | Vavuniya | North Construction (Pvt) Ltd | 5% | 25032191.25 | 36283467.53 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/42/NP/VVN | RR/RDA/12/25/42 | Veerapuram main road (veerapuram 2nd 3rd lane) | Vavuniya | Vavuniya | Yaso Engineering | 100% | 19745000 | 25380543.51 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06
RR/RDA/12/25/46/NP/VVN | RR/RDA/12/25/46 | Sinnasippikulam to neriyakulam road | Vavuniya | Vavuniya | North Construction (Pvt) Ltd | 100% | 14561522.25 | 21276360.97 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-23 | 2026-02-22
RR/RDA/12/25/53/NP/VVN | RR/RDA/12/25/53 | Ethawetunuwewa Temple Road | Vavuniya | Vavuniya | Shiyamala Construction | 100% | 9515000 | 12174775.32 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-05
RR/RDA/12/25/54/NP/VVN | RR/RDA/12/25/54 | Nikawewa Right Village Road | Vavuniya | Vavuniya | Yansika Construction | 70% | 17143053.95 | 22922029.4 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-05
RR/RDA/12/25/55/NP/VVN | RR/RDA/12/25/55 | Mayawewa to Namalpura Road | Vavuniya | Vavuniya | Yansika Construction | 100% | 17639615.95 | 22825561.83 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-05
RR/RDA/12/25/56/NP/VVN | RR/RDA/12/25/56 | From Nikawewa Post Office to Nikawewa Right Village | Vavuniya | Vavuniya | Yansika Construction | 100% | 17924713.95 | 23412051.37 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-05
RR/RDA/12/25/57/NP/VVN | RR/RDA/12/25/57 | Nikawewa Right to Sapumalthanna | Vavuniya | Vavuniya | Yansika Construction | 100% | 11848115.95 | 15184106.87 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-05
RR/RDA/12/25/58/NP/VVN | RR/RDA/12/25/58 | Preschool Road | Vavuniya | Vavuniya | 5N Group Construction | 100% | 21518222 | 28313232.5 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-10 | 2026-02-08
RR/RDA/12/25/59/NP/VVN | RR/RDA/12/25/59 | Kalyanipura 2nd lane | Vavuniya | Vavuniya | 5N Group Construction | 100% | 28184992 | 37048858.38 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-12
RR/RDA/12/25/44 |  | Menicfarm school road (0.5km) (NVVPE97) | Vavuniya | Vavuniya |  | 100% | 11100861.98 | 11100861.98 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/12/25/06 |  | Paalavinayagar road | Vavuniya | Vavuniya |  | 100% | 17373382.99 | 18688450.91 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-14 | 2025-11-13 | 2026-02-28
RR/RDA/12/25/11 |  | Madeenanagar road | Vavuniya | Vavuniya |  | 100% | 21394474.49 | 21394474.49 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-10-16 | 2025-11-01 | 2025-11-01